## Index
Index
CR-1 Project Planner
(Rev. 07/24) |  |  | FY 2025
Calendar Year 2024
Instructions | General Info | Reference | Databases | Bldg Type 1 | Bldg Type 2 | Bldg Type 3 | Estimate
Written | Executive Summary | HCI | Database | Program | Program | Program | Estimate
Flow Chart | Overview | Email capout | Tradeline | Attributes | Attributes | Attributes
| Narrative | PB Help | BITS Comp Request | Comps | Comps | Comps
| Budget |  | eVA | Blender
Drawings
Escalation Tool
Planning

## Executive Summary
Executive Summary | [5 empty] | 2024-07-16 11:25
|  | Agency: | Average Agency
|  | Project: | XYZ Hall
|  | Scope: | 208600
Capital Budget Request Amounts
|  |  | Costs at Time of Estimate |  | Escalation and Supply Chain Premium | Costs at Mid-construction **
|  |  | 2025-10-01 |  |  | 2027-10-01
| Detailed Planning Costs: |  | 3316108.5165 |  | 377765.5378 | 3693874.0543
| Construction Costs * |  | 65815034.7879 | 315.5083
| Prevailing Wage Premium Allowance |  | 3290751.7394 | 5%
| Escalation from | 2024-01-01 | to | 2024-12-31 | 2764231.4611 |  | 4%
| Escalation from | 2025-01-01 | to | 2025-12-31 | 2866769.5206 |  | 4%
| Escalation from | 2026-01-01 | to | 2028-09-30 | 8504944.738 |  | 4%
|  | Construction Sub-Total | 69105786.5273 | 331.2837 | 14135945.7197 | 83241732.247 | 399.0495
|  | Soft Costs | 11015964.309 | 15.94% | 1809443.6571 | 12825407.9662 | 15.41%
|  | FF&E: | 1954772.7273 | 9.3709 | 494044.1257 | 2448816.853 | 11.7393
|  | Acquisition: |  |  |  | 1000000
|  | Total: | 83076523.5636 | 398.2575 | 16439433.5025 | 99515957.0661 | 477.0659

## Overview
< Return to Index | [10 empty] | 0 | Start of construction
DGS-30-199 |  |  |  | CR-1 | [6 empty] | 3 | Mid-Point of Construction
(Rev. 07/24) | [10 empty] | 1 | Start Plus 1 Year
| FY 2025 Project Planner | [9 empty] | 4 | End of Construction
Note | OVERVIEW | [9 empty] | ACCESSIBILITY
| Project name | XYZ Hall | [8 empty] | ACQUISITION
| Agency | Average Agency | [8 empty] | AGRICULTURAL FACILITY
| Project Code | 12345 | [8 empty] | AIRPORT / AVIATION FACILITY
| Project Type | CLASSROOM | [8 empty] | AMPHITHEATER
| Biennium | [9 empty] | AREA LIGHTING
| Budget Round | [9 empty] | ARENA / CONVOCATION CENTER
| Request Origin | [9 empty] | ARMORY
| Project Location | Richmond, VA | [8 empty] | ATHLETIC & RECREATIONAL FACILITIES
| Facility/Campus | [9 empty] | AUDITORIUM / THEATER
| Source of Request | [9 empty] | BOILER
| Infrastructure Element | [9 empty] | BRIDGE, PEDESTRIAN
| Contains significant technology costs? | [9 empty] | BRIDGE, VEHICULAR
| Contains significant energy costs? | [9 empty] | BUS SHELTER
| Contact | [9 empty] | CAPITOL / CITY HALL
| Prevailing Wage Premium Allowance | Applicable ► |  | Yes
|  |  | Capital Budget Request Amounts | [7 empty] | CAPITOL / CITY HALL
| PROJECT BUDGET | Amount (current date) | Amount (mid-construction) | Comments | [6 empty] | CEMETERY / MAUSOLEUM
1 | Acquisition | 1000000 | 1000000 | [7 empty] | CENTRAL HEATING / COOLING PLANT
2 | Construction | 69105786.5273 | 83241732.247 | [7 empty] | CHILLER
3 | Design & Related Services | 4850624.4603 | 5619327.4683 | [7 empty] | CLASSROOM
3 | Inspection & Testing Services | 548907.8947 | 635896.1069 | [7 empty] | CLASSROOM / ASSEMBLY
3 | Project Management & Other Costs | 4234316.2235 | 4905349.746 | [7 empty] | CLASSROOM / K-12
4 | Furnishings & Movable Equipment | 1954772.7273 | 2448816.853 | [7 empty] | CLASSROOM / LABORATORY
2 | Construction Contingency | 1382115.7305 | 1664834.6449 | [7 empty] | CLASSROOM / MULTI-PURPOSE
| TOTAL PROJECT BUDGET | 83076523.5636 | 99515957.0661 | [7 empty] | CLASSROOM / OFFICE
CLASSROOM / STUDIO
| PLANNING PHASES | Amount | Comments | [7 empty] | CLASSROOM / TRAINING CENTER
3, 5, 6 | Detailed Planning Phase | 3316108.5165 | 3693874.0543 | [7 empty] | CM SERVICES
3, 5, 6 | Additional Planning to Bid Phase | 2807999.7097 | 3400752.5977 | [7 empty] | COMMUNITY CENTER
3, 5, 6 | Total Planning to Bid Phase | 6124108.2263 | 7094626.652 | [7 empty] | CONVENTION / EXHIBITION CENTER
COURTHOUSE
| SCOPE | Amount | Comments | [7 empty] | DAM
| Total square foot (per form DGS-30-219) | 208600 |  |  | Program 1: | 40257.5758 | Program 2: | 24901.5152 | Program 3: | 133333.3333 | DATA / TELECOMMUNICATIONS
| Net # of New Parking Spaces - Surface Lot | [9 empty] | DEMOLITION
| Net # of New Parking Spaces - Parking Deck | [9 empty] | DINING / FOOD SERVICE
| Site Size (acres) | [9 empty] | DOORS
DORMITORY
| SCHEDULE | Dates | Comments | [7 empty] | DORMITORY / DINING
| Start of design | 2025-10-01 | [8 empty] | ELECTRICAL
| Start of construction | 2027-10-01 | [8 empty] | ELEVATOR
| Mid-Point of Construction | 2028-09-30 | [8 empty] | EMERGENCY GENERATOR
| End of Construction | 2029-09-30 | [8 empty] | ENERGY MANAGEMENT SYSTEM
A | Annual Inflation Rate | 4% | [8 empty] | FLOORING
B1 | Supply Chain Premium 2024 | 0% | [8 empty] | ENVIRONMENTAL
B2 | Supply Chain Premium 2026 | 0% | [8 empty] | EQUIPMENT
B3 | Supply Chain Premium 2027 And After | 0% | [8 empty] | EQUIPMENT
A+B1 | Total Escalation Rate (2024) | 4% | [8 empty] | FENCING
| Baseline Date | 2025-10-01 | [8 empty] | FIRE / POLICE STATION
FIRE DETECTION & ALARM
1 | The amount required for acquisition, shown in the blue highlighted cell, does not include inflation or supply chain premium. | [9 empty] | FIRE PROTECTION
2 | The amount requried for construction, shown in the blue highlighted cell, includes inflation and supply chain premium to the mid-point of construction. | [9 empty] | FLOORING
3 | The amount required for soft costs, shown in the blue highlighted cell, includes inflation to the start of construction. | [9 empty] | FOUNDATION
4 | The amount required for FF&E, shown in the blue highlighted cell, includes inflation and supply chain premium to the end of construction. | [9 empty] | FUEL FACILITY
5 | Planning amounts are part of the overall project total. | [9 empty] | GREENHOUSE
6 | List any unusual Detailed Planning requirements in comments. | [9 empty] | HATCHERY
HAZARDOUS MATERIALS ABATEMENT
HOSPITAL / MEDICAL CENTER
HOTEL / MOTEL
HVAC
INFRASTRUCTURE
JUVENILE FACILITY
LABORATORY
LABORATORY / CLASSROOM
LIBRARY / RESOURCE CENTER
LIBRARY / STUDENT CENTER
LIFE SAFETY / FIRE SAFETY
LIGHTING
MAINTENANCE / REPAIRS
MAINTENANCE AREA
MAINTENANCE BUILDING
MAINTENANCE GARAGE
MAINTENANCE RESERVE
MANUFACTURING
MARINE CONSTRUCTION
MASONRY
MILLWORK
MISCELLANEOUS
MONUMENT
MULTI-PURPOSE
MUSEUM
NURSING / CONVALESCENT CENTER
OFFICE
OFFICE - BANK
OFFICE - HIGH RISE
OFFICE - MEDICAL OFFICE / CLINIC
OFFICE - SHELL
OFFICE - TENANT UPFITS / BUILDOUTS
OFFICE / CLASSROOM
OFFICE / INDUSTRIAL
OFFICE / OTHER
OFFICE / PARKING GARAGE
OFFICE / RESIDENTIAL
OFFICE / WAREHOUSE
PAINTING
PARK AND CAMPGROUND FACILITIES
PARKING LOT
PARKING STRUCTURE
PAVING
PEDESTRIAN TRAIL
PICNIC SHELTER
PLANNING STUDY
PLUMBING
PORT FACILITY
POWER PLANT
PRE-CONSTRUCTION
RAILROAD / RAIL FACILITIES
REGULATORY COMPLIANCE
RENOVATION, GENERAL
REPAIR SHOP
RESEARCH FACILITY
RESIDENTIAL
ROADS
ROOFING
SANITARY SEWER
SCULPTURE
SECURITY SYSTEMS
SITE DATA/TELECOMMUNICATIONS
SITE ELECTRICAL DISTRIBUTION
SITE HEATING/COOLING DISTRIBUTION
SITE UTILITIES - MISC / OTHER
SITEWORK / SITE IMPROVEMENTS
STADIUM
STAIRS
STORM SEWER / STORM WATER RETENTION
STRUCTURAL
STUDENT CENTER
SURVEY
TEMPORARY STRUCTURE
TO BE ASSIGNED 1
UNDERGROUND STORAGE TANK
VDOT - CHEMICAL BUILDING
VDOT - COMBO BUILDING
VDOT - FLAG POLES
VDOT - OFFICE/SHOP/STORAGE
VDOT - REPAIR SHOPS
VDOT - REST AREA CONCESSION
VDOT - SIGN CREW BLDG
VDOT - SPREADER RACK
VDOT - STORAGE BLDG
VDOT - TIMEKEEPER OFFICE
VDOT - TRAFFIC MANAGEMENT CTR
VDOT - TRAILER
VDOT - VENDING SHELTER
VISITORS CENTER
WAREHOUSE / OFFICE
WAREHOUSE / STORAGE
WASTEWATER TREATMENT
WATER SUPPLY / DISTRIBUTION / STORAGE
WATER TREATMENT
WATERPROOFING
WINDOWS
Biennial Bill
Amended Bill
Caboose Bill
Yes
No
Formulas:
XYZ Hall = [XYZ Hall, row above]+730
XYZ Hall = ([XYZ Hall, row above]+[XYZ Hall, row below])/2
Enter project information in yellow cells.
Program totals referenced here for convenience. Parking structure sf (Program 3 in this example) does not count as "scope" per form DGS-30-219.
Use drop-down to enter Yes/ No for applicability of Prevailing Wages Allowance for the project.
Note on AA1: Do not delete. This number is used for the escalation calculation.
Note on AA2: Do not delete. This number is used for the escalation calculation.
Note on AA3: Do not delete. This number is used for the escalation calculation.
Note on AA4: Do not delete. This number is used for the escalation calculation.
Note on C10: Pull-down list
Note on C12: Pull-down list
Note on C17: Pull-down list
Note on C18: Pull-down list
Note on C19: Pull-down list
Note on B54: Date on which this estimate is based (does not need to be today's date)

## Narrative
< Return to Index
DGS-30-199 |  | CR-1
Agency Narrative
Agency Description
Construction of a two level classroom building and renovation of an existing classroom building.
Justification
The student population has exceeded the capacity of the existing space on campus.
Alternatives Considered
Alternate schedules but that does not serve the student population well.
Costing Methodology
Comps plus supplemental estimates
Enter project information in yellow cells.

## Budget
< Return to Index
[5 empty] | Single Phase / Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6 | Phase 7 | Phase 8 | Phase 9 | Phase 10
|  |  |  | Phase Title: | Site Acquisition Phase | Phase 2: Construction Phase | Unit Price (@ Current Date)
| Description |  | Escalated Amounts | Non-Escalated Amounts | Amount | Amount | Amount | Amount | Amount | Amount | Amount | Amount | Amount | Amount |  | Comments
Site Acquisition
| Site Acquisition Total |  | 1000000 | 1000000 | 1000000
Construction
| Total From Blender |  | 83241732.247 | 69105786.5273 |  | Phase 2: 69105786.5273
| Construction Total |  | 83241732.247 | 69105786.5273 | 0 | 69105786.5273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & Related Services
| A/E Basic Services |  | 4963554.477 | 4284558.7647 |  | Phase 2: 4284558.7647
| A/E Additional Services |  | 99271.0895 | 85691.1753 |  | Phase 2: 85691.1753
| A/E Reimbursables |  | 49635.5448 | 42845.5876 |  | Phase 2: 42845.5876
| Specialty Consultants (Food Services, Acoustics, etc.) |  | 0 | 0
| CM Design Phase Services |  | 400286.6514 | 345528.9326 |  | Phase 2: 345528.9326
| Subsurface Investigation (Geotech, Soil Borings) |  | 46339.0024 | 40000 |  | Phase 2: 40000
| Land Survey |  | 13901.7007 | 12000 |  | Phase 2: 12000
| Archeological Survey |  | 46339.0024 | 40000 |  | Phase 2: 40000
| Hazmat Survey & Design |  | 0 | 0 |  | Phase 2: 0
| Value Engineering Services |  | 0 | 0 |  | Phase 2: 0
| Cost Estimating Services |  | 0 | 0 |  | Phase 2: 0
| Other Design & Related Services (list): |  | 0
|  | Environmental Impact Report (EIR) | 0 | 0 |  | Phase 2: 0
|  |  | 0 | 0
| Design & Related Services Total |  | 5619327.4683 | 4850624.4603 | 0 | 4850624.4603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.019%
Inspection & Testing Services
| Project Inspection Services (in-house or consultant) |  | 333823.7347 | 288157.8947 |  | Phase 2: 288157.8947
| Project Testing Services (conc. Steel, roofing, etc.) |  | 302072.3722 | 260750 |  | Phase 2: 260750
| Inspection & Testing Services Total |  | 635896.1069 | 548907.8947 | 0 | 548907.8947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7943%
Project Management & Other Costs
| Agency Project Management |  | 1891667.8301 | 1632894.7368 |  | Phase 2: 1632894.7368
| Work By Owner (List): |  | 0
|  | DGS Division of Real Estate services | 28961.8765 | 25000 | 25000
|  |  | 0 | 0
| DEB Services |  | 1601146.6055 | 1382115.7305 |  | Phase 2: 1382115.7305
| Advertisements |  | 6950.8504 | 6000 |  | Phase 2: 6000
| Printing & Reproduction | Abatement Design | 23169.5012 | 20000 |  | Phase 2: 20000
| Moving & Relocation Expenses | Abatement • | 115391.1372 | 99606.0606 |  | Phase 2: 99606.0606
| Data & Voice Communications |  | 379684.5827 | 327745.15 |  | Phase 2: 327745.15
| Signage |  | 150970.3637 | 130318.1818 |  | Phase 2: 130318.1818
| Demolition | Soil Borings | 231695.0122 | 200000 |  | Phase 2: 200000
| Hazardous Material Abatement | Geotechnical Report | 0 | 0
| Utility Connection Fees |  | 115847.5061 | 100000 |  | Phase 2: 100000
| Utility Relocations |  | 57923.7531 | 50000 |  | Phase 2: 50000
| Commissioning |  | 301940.7273 | 260636.3636 |  | Phase 2: 260636.3636
| Miscellaneous Other Costs (List): |  | 0
|  | Miscellaneous site acquisition soft costs | 0 | 0
|  |  | 0 | 0
| Project Management & Other Costs Total |  | 4905349.746 | 4234316.2235 | 25000 | 4209316.2235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.127%
Furnishings & Movable Equipment (FF&E)
Furnishings
|  |  | 2448816.853 | 1954772.7273 |  | Phase 2: 1954772.7273
Movable Equipment
|  |  | 0 | 0
| Furnishings & Movable Equipment (FF&E) Total |  | 2448816.853 | 1954772.7273 | 0 | 1954772.7273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Contingency | [16 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
| Construction Contingency Total |  | 1664834.6449 | 1382115.7305 | 0 | 1382115.7305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2% |  | 0 | 1382115.7305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals
| Acquisition Costs |  | 1000000 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction Costs |  | 83241732.247 | 69105786.5273 | 0 | 69105786.5273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Soft Costs (less FF&E and Acquisition Costs) |  | 12825407.9662 | 11015964.309 | 25000 | 10990964.309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.94%
| Furnishings & Movable Equipment (FF&E) |  | 2448816.853 | 1954772.7273 | 0 | 1954772.7273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Costs |  | 99515957.0661 | 83076523.5636 | 1025000 | 82051523.5636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 398.2575
Note on H11: Point to Blender Total (F20) if project has only one phase. Point to Building Type 1, 2, 3 or Estimate on Blender tab (total F column) for multiple phases.
Note on I11: Point to Building Type 1, 2, 3 or Estimate on Blender tab (total F column) for multiple phases.
Note on J11: Point to Building Type 1, 2, 3 or Estimate on Blender tab (total F column) for multiple phases.
Note on K11: Point to Building Type 1, 2, 3 or Estimate on Blender tab (total F column) for multiple phases.
Note on L11: Point to Building Type 1, 2, 3 or Estimate on Blender tab (total F column) for multiple phases.
Note on M11: Point to Building Type 1, 2, 3 or Estimate on Blender tab (total F column) for multiple phases.
Note on N11: Point to Building Type 1, 2, 3 or Estimate on Blender tab (total F column) for multiple phases.
Note on O11: Point to Building Type 1, 2, 3 or Estimate on Blender tab (total F column) for multiple phases.
Note on P11: Point to Building Type 1, 2, 3 or Estimate on Blender tab (total F column) for multiple phases.
Note on Q11: Point to Building Type 1, 2, 3 or Estimate on Blender tab (total F column) for multiple phases.
Note on H15: Const Amt: <$1m / $1m-$5m / $5m-$10m / >$10m Percentages: Gar, warehouse: 6.2 / 5.3 / 4.9 / 4.5 Edu, Lib, Off: 8 / 7 / 6.6 / 6.2 Hosp, Labs, Mus: 11.9 / 9.5 / 8.8 / 8 Increase by 30% for renovation.
Note on I15: Const Amt: <$1m / $1m-$5m / $5m-$10m / >$10m Percentages: Gar, warehouse: 6.2 / 5.3 / 4.9 / 4.5 Edu, Lib, Off: 8 / 7 / 6.6 / 6.2 Hosp, Labs, Mus: 11.9 / 9.5 / 8.8 / 8 Increase by 30% for renovation.
Note on J15: Const Amt: <$1m / $1m-$5m / $5m-$10m / >$10m Percentages: Gar, warehouse: 6.2 / 5.3 / 4.9 / 4.5 Edu, Lib, Off: 8 / 7 / 6.6 / 6.2 Hosp, Labs, Mus: 11.9 / 9.5 / 8.8 / 8 Increase by 30% for renovation.
Note on K15: Const Amt: <$1m / $1m-$5m / $5m-$10m / >$10m Percentages: Gar, warehouse: 6.2 / 5.3 / 4.9 / 4.5 Edu, Lib, Off: 8 / 7 / 6.6 / 6.2 Hosp, Labs, Mus: 11.9 / 9.5 / 8.8 / 8 Increase by 30% for renovation.
Note on L15: Const Amt: <$1m / $1m-$5m / $5m-$10m / >$10m Percentages: Gar, warehouse: 6.2 / 5.3 / 4.9 / 4.5 Edu, Lib, Off: 8 / 7 / 6.6 / 6.2 Hosp, Labs, Mus: 11.9 / 9.5 / 8.8 / 8 Increase by 30% for renovation.
Note on M15: Const Amt: <$1m / $1m-$5m / $5m-$10m / >$10m Percentages: Gar, warehouse: 6.2 / 5.3 / 4.9 / 4.5 Edu, Lib, Off: 8 / 7 / 6.6 / 6.2 Hosp, Labs, Mus: 11.9 / 9.5 / 8.8 / 8 Increase by 30% for renovation.
Note on N15: Const Amt: <$1m / $1m-$5m / $5m-$10m / >$10m Percentages: Gar, warehouse: 6.2 / 5.3 / 4.9 / 4.5 Edu, Lib, Off: 8 / 7 / 6.6 / 6.2 Hosp, Labs, Mus: 11.9 / 9.5 / 8.8 / 8 Increase by 30% for renovation.
Note on O15: Const Amt: <$1m / $1m-$5m / $5m-$10m / >$10m Percentages: Gar, warehouse: 6.2 / 5.3 / 4.9 / 4.5 Edu, Lib, Off: 8 / 7 / 6.6 / 6.2 Hosp, Labs, Mus: 11.9 / 9.5 / 8.8 / 8 Increase by 30% for renovation.
Note on P15: Const Amt: <$1m / $1m-$5m / $5m-$10m / >$10m Percentages: Gar, warehouse: 6.2 / 5.3 / 4.9 / 4.5 Edu, Lib, Off: 8 / 7 / 6.6 / 6.2 Hosp, Labs, Mus: 11.9 / 9.5 / 8.8 / 8 Increase by 30% for renovation.
Note on Q15: Const Amt: <$1m / $1m-$5m / $5m-$10m / >$10m Percentages: Gar, warehouse: 6.2 / 5.3 / 4.9 / 4.5 Edu, Lib, Off: 8 / 7 / 6.6 / 6.2 Hosp, Labs, Mus: 11.9 / 9.5 / 8.8 / 8 Increase by 30% for renovation.

## Blender
< Return to Index | [12 empty] | Hidden Column | Hidden Column | Hidden Column
[13 empty] | ($MM) Construction Cost | ($MM) Construction Cost
[13 empty] | FROM | TO | PW %
[13 empty] | 0 | 10 | 15%
| BLENDER |  |  |  |  | HIDDEN COLUMN |  |  | HIDDEN COLUMN | HIDDEN COLUMN |  |  | 10 | 30 | 10%
[13 empty] | 30 | 80 | 5%
| Project Part | Building Type | Project Type | Unit Type | Quantity | SF_CM Application | % | Unit Price | Average Area from Comps Sheet | Size Factor | *Cost Multiplier | Total | 80 | 80+ | 3%
| Building Type 1 | New Classroom Buildings | Building Construction - Quantity Unit Square Feet | Sq. Ft. | 50000 | 1 | 33.33% | 504.0075 | 126388.6667 | 1.2046 | 0.98772 | 24890973.9284
| Building Type 2 | New Office Building | Building Construction - Quantity Unit Square Feet | Sq. Ft. | 60000 | 1 | 40% | 535.6121 | 104909.25 | 1.2046 | 0.98772 | 31742161.0047
| Building Type 3 | New Parking Structure | Building Construction - Quantity Unit Square Feet | Sq. Ft. | 40000 | 1 | 26.67% | 179.5366 | 151599.375 | 1.2046 | 0.98772 | 7093293.6047
| Estimate | Other Modifications | [7 empty] | - | 1 | 2088606.25
| Sub-Total | [10 empty] | 65815034.7879
| Prevailing Wage Premium Allowance |  |  |  | Applicable ► |  | Yes | 5% |  |  |  | 3290751.7394
| Grand Total | [10 empty] | 69105786.5273
*Cost Multiplier
Cost Multiplier is a calculated coefficient multiplicable to unit price utilized for current estimation to account for size variation of the proposed project over the sizes of the projects that helped build-up the estimate unit price.

## Type 1 Prog
< Return to Index
PROGRAM
| CLASSROOM / OFFICE |  | GSF | 40257.5758
|  |  | Efficiency | 66%
|  |  | Total | 26570
CLASSROOM
| Space Type | Quantity | Net Area (sf) | Total | Comments
| 45 Seat Classroom | 5 | 1125 | 5625
| 60 Seat Classroom | 3 | 1500 | 4500
| 72 Seat Classroom | 1 | 1800 | 1800
| 100 Seat Classroom | 2 | 2500 | 5000
| Open Computer Laboratory | 4 | 1400 | 5600
| Student Collaborative Learning Spaces | 1 | 2500 | 2500
| Dean's Office | 1 | 185 | 185
| Associate Dean's Office | 1 | 160 | 160
| Professional Staff Offices | 10 | 120 | 1200
Add Spaces, Quantity, and Net Area. Specify Building Efficiency According to CPSM Section 6.1.2.4.
Note on D6: Building Efficiency Ratio per CPSM 6.1.2.4
Note on E6: Enter value for building type per CPSM 6.1.2.4

## Type 1 Attr
< Return to Index
New Construction
|  | Project Characteristics |  |  |  | Renovation
New / Ren.: | New Construction | Building Type: | CLASSROOM
H-5
A Substructure | Spread Footings | Piles |  | Ren - L | I-3
| Comments |  |  | Ren - M | I-4 |  |  | Not Required
|  |  |  | Ren - H | M |  |  | Unknown
[5 empty] | R-2 |  |  | Spread Footings
B Shell | Brick | Curtain Wall | Stone |  | R-3 |  |  | Piles
| Comments |  |  |  | R-4 |  |  | Piles & Grd Beams
[5 empty] | S-1 |  | Not Required | CIP Conc Ple Caps
CMU
C Interiors | Custom Grade | [5 empty] | Stone
| Comments | [5 empty] | Brick
Concrete
Curtain Wall
D Services | From Plant | VAV | [5 empty] | Not Required
| Comments | [6 empty] | Unknown
[7 empty] | Not Required | Other – See Comments
[7 empty] | Unknown | Standard Grade
E Equipment & Furnishings | [7 empty] | Custom Grade
| Built-In Furnishings | Special Eq. | [5 empty] | Premium Grade
| Comments |  |  |  |  | Not Required
Unknown
Built-In Furnishings
F Special Construction & Demolition | [5 empty] | Lab Eq. |  | Not Required
| Comments |  |  |  |  | Special Eq. |  | Unknown
[5 empty] | Water |  |  | Other – See Comments
[5 empty] | Existing |  |  | From Plant
Soil Conditions | Stable |  |  |  | Parking Deck | Not Required |  | Terminal & Package Units
| Comments |  |  |  |  | Unknown |  | Gas
[6 empty] | Other – See Comments |  | 4-Pipe
[6 empty] | Stable |  | VAV
Other Distignuishing Features | [7 empty] | Chiller(s)
Boiler(s)
Heat Pumps
Specify project attributes using gray pull-downs and open field yellow text boxes.
Specify project attributes using gray pull-downs and open field yellow text boxes.

## Type 1 Comps
< Return to Index
Yes
PROPOSED PROJECT | [8 empty] | No
Proposed Project Type (This part) |  |  | Building Construction - Quantity Unit Square Feet
Standard Building Category from VBCCD |  |  | CLASSROOM BUILDINGS
Standard Building Type from VBCCD |  |  | New Classroom Buildings
Building Category/ Type not in VBCCD
Project location (city): |  |  | Alexandria
HCI for proposed project: |  |  | 279.3
Cost From Database / Comparative Project
|  |  |  | Comp #1 | Comp #2 | Comp #3 | Cost From Database
No
COMPARABLE PROJECT |  |  |  | Cell $D$4 to be filled in first for the fillable form below to be available to fill.
| a. | Project title: |  | Construct New Hall 1 | Construct New Hall 2 | Construct New Hall 3 | New Classroom Buildings
| b. | Owner:
| c. | Project location: |  | Charlottesville, VA | Blacksburg, VA | Virginia Beach, VA | Richmond, VA (HCI: 257.4) | ◄Check This HCI Value
| d. | Construction contract award year: |  | 2020 | 2016 | 2010
COMPARABLE PROJECT SCOPE
| e1. | Quantity Unit of Measurement |  |  |  |  | Sq. Ft.
| e2. | Gross quantity of the comp: |  | 160784 | 71000 | 147382 | 85410
| e3. | Gross quantity for this portion of the project : |  | 50000
| f. | Key quantity (i.e.; # of beds, cells, spaces, etc.): |  | NA | NA | NA
| g. | Comments: |  | Construction Cost | Construction Cost | Construction Cost
COMPARABLE PROJECT COST (or Database average)
|  |  |  | Enter total amount | Enter total amount | Enter total amount
| h. | Total construction contract award amount: |  | 55000000 | 19841051 | 27767194
| i. | Sitework & utilities amount (if not included above):
| j. | Subtotal per GSF: |  | 342.0738 | 279.4514 | 188.4029
BRING COMP TO NEW LOCATION AND CURRENT DATE
| k. | HCI for comp (see tab): |  | 205.3 | 180 | 151.8 | 257.4 | ◄Check This HCI Value
| l. | Subtotal per GSF, adjusted for escalation and location to today: |  | 465.3737 | 433.6155 | 346.6464 | 426.2206
MODIFICATIONS TO COMPARABLE PROJECT PER GSF
Itemize modifications (plus or minus) to the comparative project's sitework, utilities, or building construction cost to make it comparable in scope, complexity, etc. to the proposed project.
|  |  | Description: | Enter amount per GSF | Enter amount per GSF | Enter amount per GSF | Enter amount per GSF
| m1. | Modification #1: | Contaminated Soil Premiums | 19.07 | 19.07 | 19.07 | 19.07
| m2. | Modification #2: | Earth Retention System & Site Logtics Prem. | 20.64 | 20.64 | 20.64 | 20.64
| m3. | Modification #3: | High Rise Premiums | 27.25 | 27.25 | 27.25 | 27.25
| m4. | Modification #4: | Urban Acoustics Premiums | 23.77 | 23.77 | 23.77 | 23.77
SUB-TOTAL OF COMP WITH MODIFICATIONS, NEW LOCATION AND CURRENT DATE |  |  |  | 556.1037 | 524.3455 | 437.3764 | 516.9506
TOTALS
| n. | Total cost per GSF: |  | 556.1037 | 524.3455 | 437.3764 | 516.9506
| o. | Average Cost Per GSF: |  | 504.0075
Click for Database Summary with Building Categories and Types
Make selection from dropdowns -
in order (2 before 3)
Make selection
from drop down
Enter GSF
for this part of
the current project
Median GSF from VBCCD (database) is pre-populated.

## Cost Multiplier (hidden)
LINK TO >> Square Foot Project Size Modiﬁer
[10 empty] | Project Type (ths part) - Quantity Unit | SF_CM Application
[10 empty] | Building Construction - Quantity Unit Square Feet | 1
[10 empty] | Parking - Quantity Unit Square Feet | 1
[10 empty] | Parking - Quantity Unit Spaces | 0
[10 empty] | Others (like utility, site development etc.) | 0
|  | Two Curves |  |  |  |  | Three Curves
|  | Calculation Testing |  |  |  |  | Calculation Testing
|  | Size Factor |  | 1.2046 |  |  | Size Factor |  | 1.2046
|  | Cost Multiplier |  | 0.98424 |  |  | Cost Multiplier |  | 0.98772
|  | x | y
| Size Factor range | Size Factor | Cost Multiplier | Slope | Intercept | Equation | Size Factor range | Equation
| SF<0.5 | <0.5 | 0.9 |  |  |  | SF<0.5
| 0.5<=SF<1 | 0.5 | 1.1 | -0.2 | 1.2 | =Intercept+Slope*SF | 0.5<=SF<1 | =Intercept+Slope*SF
| 0.5<=SF<1 | 1 | 1 |  |  |  | 0.5<=SF<1
| 1 | 1 | 1 |  |  |  | 1
| 1<=SF<3.5 | 1 | 1 |  |  | =1.0311-0.0389*SF | 1<=SF<3.5
| 1<=SF<3.5 | 2 | 0.94 |  |  |  | 1<=SF<3.5 | =1.06-0.06*SF
| 1<=SF<3.5 | 3.5 | 0.9 |  |  |  | 1<=SF<3.5 | 0.9933-0.067*SF

## Type 2 Prog
< Return to Index
PROGRAM
| CLASSROOM / OFFICE |  | GSF | 24901.5152
|  |  | Efficiency | 66%
|  |  | Total | 16435
CLASSROOM
| Space Type | Quantity | Net Area (sf) | Total | Comments
| Maker Lab | 4 | 2000 | 8000
| Loading Dock | 1 | 2000 | 2000
| Conference Room | 3 | 240 | 720
| General Storage | 2 | 120 | 240
| IT Storage/Work Room | 1 | 245 | 245
| Restrooms | 12 | 240 | 2880
| Cyber Café | 1 | 1000 | 1000
| Vending & Seating Area | 3 | 450 | 1350
Add Spaces, Quantity, and Net Area. Specify Building Efficiency According to CPSM Section 6.1.2.4.
Note on D6: Building Efficiency Ratio per CPSM 6.1.2.4
Note on E6: Enter value for building type per CPSM 6.1.2.4

## Type 2 Attr
< Return to Index
New Construction
|  | Project Characteristics |  |  |  | Renovation
New / Ren.: | Renovation | Building Type: | CLASSROOM
H-5
A Substructure |  |  |  | Ren - L | I-3
| Comments |  |  | Ren - M | I-4 |  |  | Not Required
|  |  |  | Ren - H | M |  |  | Unknown
[5 empty] | R-2 |  |  | Spread Footings
B Shell | Brick |  |  |  | R-3 |  |  | Piles
| Comments |  |  |  | R-4 |  |  | Piles & Grd Beams
[5 empty] | S-1 |  | Not Required | CIP Conc Ple Caps
CMU
C Interiors | Custom Grade | [5 empty] | Stone
| Comments | [5 empty] | Brick
Concrete
Curtain Wall
D Services | [7 empty] | Not Required
| Comments | [6 empty] | Unknown
[7 empty] | Not Required | Other – See Comments
[7 empty] | Unknown | Standard Grade
E Equipment & Furnishings | [7 empty] | Custom Grade
Premium Grade
| Comments |  |  |  |  | Not Required
Unknown
Built-In Furnishings
F Special Construction & Demolition | [5 empty] | Lab Eq. |  | Not Required
| Comments |  |  |  |  | Special Eq. |  | Unknown
[5 empty] | Water |  |  | Other – See Comments
[5 empty] | Existing |  |  | From Plant
Soil Conditions |  |  |  |  | Parking Deck | Not Required |  | Terminal & Package Units
| Comments |  |  |  |  | Unknown |  | Gas
[6 empty] | Other – See Comments |  | 4-Pipe
[6 empty] | Stable |  | VAV
Other Distignuishing Features | [7 empty] | Chiller(s)
Boiler(s)
Heat Pumps
Specify project attributes using gray pull-downs and open field yellow text boxes.
Specify project attributes using gray pull-downs and open field yellow text boxes.

## Type 2 Comps
< Return to Index
Yes
PROPOSED PROJECT | [8 empty] | No
Proposed Project Type (This part) |  |  | Building Construction - Quantity Unit Square Feet
Standard Building Category from VBCCD |  |  | OFFICE BUILDINGS
Standard Building Type from VBCCD |  |  | New Office Building
Building Category/ Type not in VBCCD
Project location (city): |  |  | Alexandria
HCI for proposed project: |  |  | 279.3
Cost From Database / Comparative Project
|  |  |  | Comp #1 | Comp #2 | Comp #3 | Cost From Database
COMPARABLE PROJECT |  |  |  | Cell $D$4 to be filled in first for the fillable form below to be available to fill.
| a. | Project title: |  | Renovate B Hall | Renovate C Hall | Renovate D Hall | New Office Building
| b. | Owner: |  | GBU | HU | WU
| c. | Project location: |  | Green Bay, WI | Hampton, VA | Williamsburg, VA | Richmond, VA (HCI: 257.4) | ◄Check This HCI Value
| d. | Construction contract award year: |  | 2020 | 2016 | 2010
COMPARABLE PROJECT SCOPE
| e1. | Quantity Unit of Measurement |  | Sq. Ft. |  |  | Sq. Ft.
| e2. | Gross quantity of the comp: |  | 146789 | 141014 | 131834 | 13538
| e3. | Gross quantity for this portion of the project : |  | 60000
| f. | Key quantity (i.e.; # of beds, cells, spaces, etc.): |  | NA | NA | NA
| g. | Comments: |  | Construction Cost | Construction Cost | Construction Cost
COMPARABLE PROJECT COST (or Database average)
|  |  |  | Enter total amount | Enter total amount | Enter total amount
| h. | Total construction contract award amount: |  | 52000000 | 35000000 | 33500000
| i. | Sitework & utilities amount (if not included above):
| j. | Subtotal per GSF: |  | 354.25 | 248.2023 | 254.1074
BRING COMP TO NEW LOCATION AND CURRENT DATE
| k. | HCI for comp (see tab): |  | 205.3 | 180 | 151.8 | 257.4 | ◄Check This HCI Value
| l. | Subtotal per GSF, adjusted for escalation and location to today: |  | 481.9387 | 385.1272 | 467.5376 | 450.8234
MODIFICATIONS TO COMPARABLE PROJECT PER GSF
Itemize modifications (plus or minus) to the comparative project's sitework, utilities, or building construction cost to make it comparable in scope, complexity, etc. to the proposed project.
|  |  | Description: | Enter amount per GSF | Enter amount per GSF | Enter amount per GSF | Enter amount per GSF
| m1. | Modification #1: | Contaminated Soil Premiums | 19.07 | 19.07 | 19.07 | 19.07
| m2. | Modification #2: | Earth Retention System & Site Logtics Prem. | 20.64 | 20.64 | 20.64 | 20.64
| m3. | Modification #3: | High Rise Premiums | 27.25 | 27.25 | 27.25 | 27.25
| m4. | Modification #4: | Urban Acoustics Premiums | 23.77 | 23.77 | 23.77 | 23.77
SUB-TOTAL OF COMP WITH MODIFICATIONS, NEW LOCATION AND CURRENT DATE |  |  |  | 572.6687 | 475.8572 | 558.2676 | 541.5534
TOTALS
| n. | Total cost per GSF: |  | 572.6687 | 475.8572 | 558.2676 | 541.5534
| o. | Average Cost Per GSF: |  | 535.6121
Click for Database Summary with Building Categories and Types
Make selection from dropdowns -
in order (2 before 3)
Make selection
from drop down
Enter GSF
for this part of
the current project
Median GSF from VBCCD (database) is pre-populated.

## Type 3 Prog
< Return to Index
PROGRAM
| Parking Structure |  | GSF | 133333.3333
|  |  | Efficiency | 60%
|  |  | Total | 80000
PARKING STRUCTURE
| Space Type | Quantity | Net Area (sf) | Total | Comments
| Parking spaces | 400 | 200 | 80000
Add Spaces, Quantity, and Net Area. Specify Building Efficiency According to CPSM Section 6.1.2.4.
Note on D6: Building Efficiency Ratio per CPSM 6.1.2.4
Note on E6: Enter value for building type per CPSM 6.1.2.4

## Type 3 Attr
< Return to Index
New Construction
|  | Project Characteristics |  |  |  | Renovation
New / Ren.: | New Construction | Building Type: | PARKING STRUCTURE
H-5
A Substructure | Spread Footings |  |  | Ren - L | I-3
| Comments |  |  | Ren - M | I-4 |  |  | Not Required
|  |  |  | Ren - H | M |  |  | Unknown
[5 empty] | R-2 |  |  | Spread Footings
B Shell | Concrete | Brick |  |  | R-3 |  |  | Piles
| Comments |  |  |  | R-4 |  |  | Piles & Grd Beams
[5 empty] | S-1 |  | Not Required | CIP Conc Ple Caps
CMU
C Interiors | [6 empty] | Stone
| Comments | [5 empty] | Brick
Concrete
Curtain Wall
D Services | [7 empty] | Not Required
| Comments | [6 empty] | Unknown
[7 empty] | Not Required | Other – See Comments
[7 empty] | Unknown | Standard Grade
E Equipment & Furnishings | [7 empty] | Custom Grade
Premium Grade
| Comments |  |  |  |  | Not Required
Unknown
Built-In Furnishings
F Special Construction & Demolition | [5 empty] | Lab Eq. |  | Not Required
| Comments |  |  |  |  | Special Eq. |  | Unknown
[5 empty] | Water |  |  | Other – See Comments
[5 empty] | Existing |  |  | From Plant
Soil Conditions |  |  |  |  | Parking Deck | Not Required |  | Terminal & Package Units
| Comments |  |  |  |  | Unknown |  | Gas
[6 empty] | Other – See Comments |  | 4-Pipe
[6 empty] | Stable |  | VAV
Other Distignuishing Features | [7 empty] | Chiller(s)
Boiler(s)
Heat Pumps
Specify project attributes using gray pull-downs and open field yellow text boxes.
Specify project attributes using gray pull-downs and open field yellow text boxes.

## Type 3 Comps
< Return to Index
Yes
PROPOSED PROJECT | [8 empty] | No
1) Proposed Project Type |  |  | Building Construction - Quantity Unit Square Feet
2) Standard Building Category from VBCCD |  |  | PARKING STRUCTURE
3) Standard Building Type from VBCCD |  |  | New Parking Structure
Building Category/Type if not in VBCCD
Project location (city): |  |  | Alexandria
HCI for proposed project: |  |  | 279.3
Cost From Database / Comparative Project
|  |  |  | Comp #1 | Comp #2 | Comp #3 | Cost From Database
Yes
COMPARABLE PROJECT |  |  |  | Cell $D$4 to be filled in first for the fillable form below to be available to fill.
| a. | Project title: |  | New Parking Deck | New Parking Deck | New Parking Deck | New Parking Structure
| b. | Owner: |  | GBU | HU | WU
| c. | Project location: |  | Green Bay, WI | Hampton, VA | Williamsburg, VA | Richmond, VA (HCI: 257.4) | ◄Verify HCI Value (see HCI tab)
| d. | Construction contract award year: |  | 2020 | 2016 | 2010
COMPARABLE PROJECT SCOPE
| e1. | Quantity Unit of Measurement |  |  |  |  | Sq. Ft.
| e2. | Gross quantity of the comp: |  | 145682 | 79853 | 132584 | 248278.5
| e3. | Gross quantity for this portion of the project : |  | 40000
| f. | Key quantity (i.e.; # of beds, cells, spaces, etc.): |  | NA | NA | NA
| g. | Comments: |  | Construction Cost | Construction Cost | Construction Cost
COMPARABLE PROJECT COST (or Database average)
|  |  |  | Enter total amount | Enter total amount | Enter total amount
| h. | Total construction contract award amount: |  | 9675000 | 4500000 | 6650000
| i. | Sitework & utilities amount (if not included above):
| j. | Subtotal per GSF: |  | 66.4118 | 56.3535 | 50.1569
BRING COMP TO NEW LOCATION AND CURRENT DATE
| k. | HCI for comp (see tab): |  | 205.3 | 180 | 151.8 | 257.4 | ◄Check This HCI Value
| l. | Subtotal per GSF, adjusted for escalation and location to today: |  | 90.3498 | 87.4419 | 92.2847 | 86.4828
MODIFICATIONS TO COMPARABLE PROJECT PER GSF
Itemize modifications (plus or minus) to the comparative project's sitework, utilities, or building construction cost to make it comparable in scope, complexity, etc. to the proposed project.
|  |  | Description: | Enter amount per GSF | Enter amount per GSF | Enter amount per GSF | Enter amount per GSF
| m1. | Modification #1: | Contaminated Soil Premiums | 19.07 | 19.07 | 19.07 | 19.07
| m2. | Modification #2: | Earth Retention System & Site Logtics Prem. | 20.64 | 20.64 | 20.64 | 20.64
| m3. | Modification #3: | High Rise Premiums | 27.25 | 27.25 | 27.25 | 27.25
| m4. | Modification #4: | Urban Acoustics Premiums | 23.77 | 23.77 | 23.77 | 23.77
SUB-TOTAL OF COMP WITH MODIFICATIONS, NEW LOCATION AND CURRENT DATE |  |  |  | 181.0798 | 178.1719 | 183.0147 | 177.2128
TOTALS
| n. | Total cost per GSF: |  | 181.0798 | 178.1719 | 183.0147 | 177.2128
| o. | Average Cost Per GSF: |  | 179.5366
Enter GSF
for this part of
the current project
Click for Database Summary with Building Categories and Types
Make selection from dropdowns -
in order (2 before 3)
Make selection
from drop down
Median GSF from VBCCD (database) is pre-populated.

## Estimate
< Return to Index
ESTIMATE
| Soil remediation at parking deck site and landscape/hardscape between addition/renovation and parking deck |  |  | Grand Total | 2088606.25
|  |  |  | Markup | 25%
|  |  |  | Sub-Total | 1670885
| Description / Location of Work | Quantity | Units | Unit Price | Total
Soil remediation
| Remove unsuitable soil | 45000 | cy | 7 | 315000
| Install structural fill | 45000 | cy | 28 | 1260000
Landscaping
| Excavation | 1 | ea | 2200 | 2200
| Soil | 5 | cy | 85 | 425
| Shrub (allowance) | 1 | ea | 5000 | 5000
| Sod | 10000 | sf | 3 | 30000
| Mulch | 10000 | sf | 2 | 20000
| Cleanup | 1 | ea | 2000 | 2000
Hardscaping
| Excavation | 1 | ea | 8500 | 8500
| Gravel | 40 | cy | 50 | 2000
| Stamped concrete | 1080 | sf | 22 | 23760
| Cleanup | 1 | ea | 2000 | 2000
Enter estimate information in yellow cells.
Enter estimate information in yellow cells.
Note on F6: Enter markup for Overhead, Profit, Insurance, Taxes, and General Conditions. Typical value: 1.25

## VBCCD Table (hidden)
Sheet Position in VBBCCD | Building Category | VBCCD Tabs Name | SUMMARY Sheet Name | # of Comps | Update Done | To be added to Summary | Cost Modifier | Quantity Unit | Quantity Range | Median Quantity | Median Cost/Sq.ft. | Match
20 | CLASSROOM BUILDINGS | New CR | New Classroom Buildings | 20 | Yes | Yes | Yes | Sq. Ft. | 21,686-280,617 | 85410 | 392.8005 |  | Row Labels | Count of VBCCD Tabs Name | VBCCD Building Types Count
21 | CLASSROOM BUILDINGS | Ren CR - L | Renovate Classroom Buildings - L | 8 | Yes | Yes | Yes | Sq. Ft. | 1,670-54,666 | 7140 | 34.9265 |  | CLASSROOM BUILDINGS | 5 | 5
22 | CLASSROOM BUILDINGS | Ren CR - M | Renovate Classroom Buildings - M | 7 | Yes | Yes | Yes | Sq. Ft. | 7,804-64,750 | 26620 | 255.3978 |  | COURTS | 1 | 1
23 | CLASSROOM BUILDINGS | Ren CR - H | Renovate Classroom Buildings - H | 15 | Yes | Yes | Yes | Sq. Ft. | 13,786-210,903 | 43436 | 426.2928 |  | DORMITORY | 3 | 3
24 | CLASSROOM BUILDINGS | Ren CR - Historic | Renovate Classroom Buildings - Historic | 10 | Yes | Yes | Yes | Sq. Ft. | 13,717-159,129 | 29832 | 347.1351 |  | DRY LABS Physics Buildings, Engineering Buildings | 7 | 7
25 | COURTS | Ren Court | Ren Court | 4 | Yes | Yes | Yes | Sq. Ft. | 29,900-44,826 | 32700 | 226.5638 |  | FOOD | 2 | 2
26 | DORMITORY | New Dorm | New Dormitory | 12 | Yes | Yes | Yes | Sq. Ft. | 59,307-216,770 | 141750 | 328.2645 |  | GYM-PHYS-ED BUILDINGS | 2 | 2
26 | DORMITORY | Ren Dorm | Renovate Dormitory | 4 | Yes | Yes | Yes | Sq. Ft. | 46,500 - 106,500 | 57159.5 | 281.4241 |  | LIBRARIES | 2 | 2
28 | DORMITORY | Ren Dorm - Historic | Renovate Dormitory - Historic | 4 | Yes | Yes | Yes | Sq. Ft. | 36,244-50,986 | 42540 | 386.3832 |  | MEDICAL | 2 | 2
34 | DRY LABS Physics Buildings, Engineering Buildings | New Dry Labs - L | New Dry Lab - L | 4 | Yes | Yes | Yes | Sq. Ft. | 50,501-161,100 | 64078 | 484.1699 |  | MULTIPURPOSE BUILDINGS | 2 | 2
35 | DRY LABS Physics Buildings, Engineering Buildings | New Dry Labs - M | New Dry Lab - M | 10 | Yes | Yes | Yes | Sq. Ft. | 26,000-161,100 | 64834.5 | 490.9503 |  | MUSEUMS | 3 | 3
36 | DRY LABS Physics Buildings, Engineering Buildings | New Dry Labs - H | New Dry Lab - H | 4 | Yes | Yes | Yes | Sq. Ft. | 50,501-200,000 | 156326.5 | 470.5011 |  | OFFICE BUILDINGS | 7 | 7
37 | DRY LABS Physics Buildings, Engineering Buildings | New Dry Lab - Automotive | New Dry Lab - Automotive | 1 | Yes | Yes | Yes | Sq. Ft. | 30,670-30,670 | 30670 | 386.0435 |  | Other | 5 | 5
38 | DRY LABS Physics Buildings, Engineering Buildings | Ren Dry Lab - L | Ren. Dry Lab - L | 3 | Yes | Yes | Yes | Sq. Ft. | 13,190-46,534 | 17450 | 135.7985 |  | PARKING | 1 | 1
39 | DRY LABS Physics Buildings, Engineering Buildings | Ren Dry Lab - M | Ren. Dry Lab - M | 4 | Yes | Yes | Yes | Sq. Ft. | 4,600-68,000 | 9281.5 | 359.2733 |  | PARKING STRUCTURE | 1 | 1
40 | DRY LABS Physics Buildings, Engineering Buildings | Ren Dry Lab - H | Ren. Dry Lab - H | 5 | Yes | Yes | Yes | Sq. Ft. | 2,950-41,452 | 5373 | 426.5432 |  | RESEARCH LABS | 3 | 3
29 | FOOD | New Dining Hall | New Dining Hall | 5 | Yes | Yes | Yes | Sq. Ft. | 7,550-115,985 | 38295 | 891.2047 |  | ROOFING | 1 | 1
30 | FOOD | Ren Dining Hall | Renovate Dining Hall | 11 | Yes | Yes | Yes | Sq. Ft. | 1,002-42,313 | 12200 | 202.944 |  | STUDENT CENTERS | 2 | 2
32 | GYM-PHYS-ED BUILDINGS | New Gym | New Gymnasium | 7 | Yes | Yes | Yes | Sq. Ft. | 16,912-110,000 | 52944 | 543.4959 |  | THEATERS | 6 | 6
33 | GYM-PHYS-ED BUILDINGS | Ren Gym | Renovate Gymnasium | 3 | Yes | Yes | Yes | Sq. Ft. | 16,353-94,486 | 30027 | 569.1493 |  | UNIVERSITY WELCOME CENTERS | 1 | 1
47 | LIBRARIES | New Libraries | New Library | 8 | Yes | Yes | Yes | Sq. Ft. | 36,710-200,000 | 126026.5 | 423.7329 |  | WET LABS Chemistry Buildings, Biology Buildings | 3 | 3
48 | LIBRARIES | Ren Libraries | Ren Library | 3 | Yes | Yes | Yes | Sq. Ft. | 1,202-15,531 | 11660 | 171.3097 |  | Grand Total | 59 | 59
50 | MEDICAL | New Mental Health Facility | New Mental Health Facility | 4 | Yes | Yes | Yes | Sq. Ft. | 117,000-430,000 | 327253.5 | 652.2819
53 | MEDICAL | Ren Medical | Ren Medical | 8 | Yes | Yes | Yes | Sq. Ft. | 7,594-94,039 | 14023.5 | 372.6418
54 | MULTIPURPOSE BUILDINGS | Multipurpose Center | New Multipurpose Center | 7 | Yes | Yes | Yes | Sq. Ft. | 11,766-167,874 | 52944 | 543.4959
55 | MULTIPURPOSE BUILDINGS | Recreation Center | Recreation Center | 14 | Yes | Yes | Yes | Sq. Ft. | 1,639-142,843 | 35842.5 | 491.9571
56 | MUSEUMS | New Museums | New Museum | 6 | Yes | Yes | Yes | Sq. Ft. | 4,405-449,000 | 64084 | 422.5243
57 | MUSEUMS | Ren Museums | Ren. Museum | 3 | Yes | Yes | Yes | Sq. Ft. | 5,000-16,000 | 6100 | 232.2019
58 | MUSEUMS | Museums - Replica | Museum - Replicas | 3 | Yes | Yes | Yes | Sq. Ft. | 3,538-30,000 | 7330 | 101.5771
9 | OFFICE BUILDINGS | Office Tenant Upfit - M | Office Tenant Upfit - M | 5 | Yes | Yes | Yes | Sq. Ft. | 11,000-20,244 | 13500 | 114.7632
59 | OFFICE BUILDINGS | New Office Building | New Office Building | 11 | Yes | Yes | Yes | Sq. Ft. | 3,200-105,000 | 13538 | 415.4742
60 | OFFICE BUILDINGS | New Small Off Add | New Small Office Addition | 6 | Yes | Yes | Yes | Sq. Ft. | 1,933-15,684 | 4684 | 256.0348
61 | OFFICE BUILDINGS | New-Ren Office 50-50 | New/Ren Office 50-50 | 6 | Yes | Yes | Yes | Sq. Ft. | 1,643-50,000 | 7903.5 | 313.9819
62 | OFFICE BUILDINGS | Ren Office - L | Ren. Office - L | 6 | Yes | Yes | Yes | Sq. Ft. | 7,500-163,935 | 118000 | 29.5631
63 | OFFICE BUILDINGS | Ren Office - M | Ren. Office - M | 6 | Yes | Yes | Yes | Sq. Ft. | 1,933-163,935 | 31370 | 205.8432
64 | OFFICE BUILDINGS | Ren Office - H | Ren. Office - H | 7 | Yes | Yes | Yes | Sq. Ft. | 9,730-163,935 | 33935 | 278.3449
82 | Other | Shooting Range | Shooting Range | 2 | Yes | Yes | Yes | Sq. Ft. | 10,000-20,976 | 15488 | 255.1564
83 | Other | Oyster Hatcheries | Oyster Hatcheries | 2 | Yes | Yes | Yes | Sq. Ft. | 11,704-62,800 | 37252 | 770.8189
84 | Other | New Police Station | New Police Station | 6 | Yes | Yes | Yes | Sq. Ft. | 1,933-97,866 | 15700 | 391.5491
101 | Other | New Vocational Labs | New Vocational Labs | 3 | Yes | Yes | Yes | Sq. Ft. | 26,000-60,000 | 30145 | 601.771
102 | Other | Maintenance Buildings | Maintenance Buildings | 10 | Yes | Yes | Yes | Sq. Ft. | 4,200-14,991 | 5731 | 290.5042
65 | PARKING | Parking | New Parking (surface lots) | 13 | Yes | Yes | No | Spaces | 94-520 | 199 | 3342.1665
67 | PARKING STRUCTURE | Parking Structure | New Parking Structure | 12 | Yes | Yes | Yes | Sq. Ft. | 102,455-840,000 | 248278.5 | 79.7016
44 | RESEARCH LABS | Research Labs | Research Labs | 8 | Yes | Yes | Yes | Sq. Ft. | 15,014-100,000 | 41935.5 | 919.5539
45 | RESEARCH LABS | Research Lab Additions | Research Lab Additions | 2 | Yes | Yes | Yes | Sq. Ft. | 4,190-15,014 | 9602 | 981.3282
46 | RESEARCH LABS | Research Lab Renovations - H | Research Lab Renovations - H | 7 | Yes | Yes | Yes | Sq. Ft. | 2,782-30,514 | 10500 | 1110.9804
68 | ROOFING | Roofing | Roof Replacement | 32 | Yes | Yes | Yes | Sq. Ft. | 2,843-422,170 | 35837 | 10.777
69 | STUDENT CENTERS | Student Centers | New Student Centers | 8 | Yes | Yes | Yes | Sq. Ft. | 6,800-177,362 | 78750 | 386.5832
70 | STUDENT CENTERS | Ren Student Centers | Ren Student Centers | 3 | Yes | Yes | Yes | Sq. Ft. | 24,150-113,531 | 44930 | 154.0562
71 | THEATERS | New Theaters | New Theater | 5 | Yes | Yes | Yes | Sq. Ft. | 5,063-41,983 | 23500 | 533.6595
72 | THEATERS | Ren Theaters - L | Ren. Theater - L | 1 | Yes | Yes | Yes | Sq. Ft. | 40,000-40,000 | 40000 | 44.0885
73 | THEATERS | Ren Theaters - M | Ren. Theater - M | 2 | Yes | Yes | Yes | Sq. Ft. | 27,600-40,000 | 33800 | 138.9314
74 | THEATERS | Ren Theaters - H | Ren. Theater - H | 2 | Yes | Yes | Yes | Sq. Ft. | 27,600-48,929 | 38264.5 | 331.2404
75 | THEATERS | Fine Arts Centers | Fine Arts Center | 5 | Yes | Yes | Yes | Sq. Ft. | 23,500-147,382 | 60000 | 511.0609
76 | THEATERS | Performing Arts Centers | Performing Arts Center | 5 | Yes | Yes | Yes | Sq. Ft. | 48,158-147,382 | 81386 | 674.8167
80 | UNIVERSITY WELCOME CENTERS | Visitors Centers | Visitor's Centers | 13 | Yes | Yes | Yes | Sq. Ft. | 3,264-39,103 | 4463 | 272.5671
41 | WET LABS Chemistry Buildings, Biology Buildings | New Wet Labs - M | New Wet Lab - M | 10 | Yes | Yes | Yes | Sq. Ft. | 2,304-116,791 | 23833.5 | 354.7563
42 | WET LABS Chemistry Buildings, Biology Buildings | New Wet Labs - H | New Wet Lab - H | 11 | Yes | Yes | Yes | Sq. Ft. | 2,304-174,195 | 90853 | 457.4949
43 | WET LABS Chemistry Buildings, Biology Buildings | Ren Wet Labs | Renovate Wet Lab - H | 11 | Yes | Yes | Yes | Sq. Ft. | 2,782-160,000 | 18274 | 385.313

## VBCCD BldgTypes
Virginia Building Construction Cost Database
|  | 5 | 1 | 3 | 2 | 2 | 7 | 3 | 3 | 2 | 2 | 2 | 3 | 7 | 1 | 1 | 1 | 2 | 6 | 5 | 1
# | Concatenate | CLASSROOM BUILDINGS | COURTS | DORMITORY | FOOD | GYM-PHYS-ED BUILDINGS | DRY LABS Physics Buildings, Engineering Buildings | WET LABS Chemistry Buildings, Biology Buildings | RESEARCH LABS | LIBRARIES | MEDICAL | MULTIPURPOSE BUILDINGS | MUSEUMS | OFFICE BUILDINGS | PARKING | PARKING STRUCTURE | ROOFING | STUDENT CENTERS | THEATERS | Other | UNIVERSITY WELCOME CENTERS
1 | New Classroom BuildingsRen CourtNew DormitoryNew Dining HallNew GymnasiumNew Dry Lab - LNew Wet Lab - MResearch LabsNew LibraryNew Mental Health FacilityNew Multipurpose CenterNew MuseumNew Office BuildingNew Parking (surface lots)New Parking StructureRoof ReplacementNew Student CentersNew TheaterShooting RangeVisitor's Centers | New Classroom Buildings | Ren Court | New Dormitory | New Dining Hall | New Gymnasium | New Dry Lab - L | New Wet Lab - M | Research Labs | New Library | New Mental Health Facility | New Multipurpose Center | New Museum | New Office Building | New Parking (surface lots) | New Parking Structure | Roof Replacement | New Student Centers | New Theater | Shooting Range | Visitor's Centers
2 | Renovate Classroom Buildings - LRenovate DormitoryRenovate Dining HallRenovate GymnasiumNew Dry Lab - MNew Wet Lab - HResearch Lab AdditionsRen LibraryRen MedicalRecreation CenterRen. MuseumNew Small Office AdditionRen Student CentersRen. Theater - LOyster Hatcheries | Renovate Classroom Buildings - L |  | Renovate Dormitory | Renovate Dining Hall | Renovate Gymnasium | New Dry Lab - M | New Wet Lab - H | Research Lab Additions | Ren Library | Ren Medical | Recreation Center | Ren. Museum | New Small Office Addition |  |  |  | Ren Student Centers | Ren. Theater - L | Oyster Hatcheries
3 | Renovate Classroom Buildings - MRenovate Dormitory - HistoricNew Dry Lab - HRenovate Wet Lab - HResearch Lab Renovations - HMuseum - ReplicasNew/Ren Office 50-50Ren. Theater - MNew Police Station | Renovate Classroom Buildings - M |  | Renovate Dormitory - Historic |  |  | New Dry Lab - H | Renovate Wet Lab - H | Research Lab Renovations - H |  |  |  | Museum - Replicas | New/Ren Office 50-50 |  |  |  |  | Ren. Theater - M | New Police Station
4 | Renovate Classroom Buildings - HNew Dry Lab - AutomotiveRen. Office - LRen. Theater - HNew Vocational Labs | Renovate Classroom Buildings - H |  |  |  |  | New Dry Lab - Automotive | [6 empty] | Ren. Office - L |  |  |  |  | Ren. Theater - H | New Vocational Labs
5 | Renovate Classroom Buildings - HistoricRen. Dry Lab - LRen. Office - MFine Arts CenterMaintenance Buildings | Renovate Classroom Buildings - Historic |  |  |  |  | Ren. Dry Lab - L | [6 empty] | Ren. Office - M |  |  |  |  | Fine Arts Center | Maintenance Buildings
6 | Ren. Dry Lab - MRen. Office - HPerforming Arts Center | [5 empty] | Ren. Dry Lab - M | [6 empty] | Ren. Office - H |  |  |  |  | Performing Arts Center
7 | Ren. Dry Lab - HOffice Tenant Upfit - M | [5 empty] | Ren. Dry Lab - H | [6 empty] | Office Tenant Upfit - M
Total |  | 5 | 1 | 3 | 2 | 2 | 7 | 3 | 3 | 2 | 2 | 2 | 3 | 7 | 1 | 1 | 1 | 2 | 6 | 5 | 1
Click for Database Summary with Building Categories and Types

## DWGs
< Return to Index
Drawings
Add drawings, sketches, or diagrams here to show intent.

## HCI
< Return to Index
Historical Cost Index |  | Latest HCI Update Year (table below) |  |  | 2024 | [178 empty] | From RSMeans, Historical Cost Index Data 2024 Copyright Gordian. 30 Patewood Dr. Suite 350, Greenville, SC, 29615; All rights reserved
From RSMeans, Historical Cost Index Data 2024 Copyright Gordian. 30 Patewood Dr. Suite 350, Greenville, SC, 29615; All rights reserved | Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | Williamsburg and Fredericksburg are not from RSMeans. The Williamsburg HCI is an average of Richmond and Newport News and the Fredericksburg HCI is an average of Richmond and Alexandria. |  | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll► | ◄Scroll
| Alabama |  |  |  |  | Alaska | Arizona |  | Arkansas |  | California | [11 empty] | Colorado |  |  | Connecticut | [7 empty] | Delaware | D.C. | Florida | [5 empty] | Georgia |  |  |  |  | Hawaii | Idaho |  | Illinois | [5 empty] | Indiana | [7 empty] | Iowa |  |  |  |  | Kansas |  | Kentucky |  | Lousiana |  |  |  | Maine |  | Maryland | Massachusetts | [8 empty] | Michigan | [7 empty] | Minesota |  |  | Mississippi |  | Misouri |  |  |  | Montana |  | Nebraska |  | Nevada |  | New Hampshire |  | New Jersey |  |  |  |  | NM | New York | [8 empty] | North Carolina |  |  |  |  | N. Dakota | Ohio | [9 empty] | Oklahoma |  |  | Oregon |  | Pennsylvania | [6 empty] | RI | South Carolina |  | South Dakota |  | Tennessee |  |  |  | Texas | [13 empty] | Utah |  | Vermont |  | Virginia | [6 empty] | Washington |  |  | West Virginia |  | Wisconsin |  |  |  |  | Wyoming | Canada
| Birming- ham | Hunts- ville | Mobile | Mont- gomery | Tusca- losa | Anchor- age | Phoenix | Tuscon | Fort Smith | Little Rock | Anaheim | Bakers- field | Fresno | Los Angeles | Oxnard | River- side | Sacra- mento | San Diego | San Francisco | Santa Barbara | Stockton | Vallejo | Colorado Springs | Denver | Pueblo | Bridge- port | Bristol | Hartford | New Britain | New Haven | Norwalk | Stamford | Water- bury | Wilming- ton | Washing- ton | Fort Lau- derdale | Jackson- ville | Miami | Orlando | Talla- hassee | Tampa | Albany | Atlanta | Colum- bus | Macon | Savan- nah | Hono- lulu | Boise | Poca- tello | Chicago | Decatur | Joliet | Peoria | Rock- ford | Spring- field | Ander- son | Evans- ville | Fort Wayne | Gary | Indian- apolis | Muncie | South Bend | Terre Haute | Cedar Rapids | Daven- port | Des Moines | Sioux City | Water- loo | Topeka | Wichita | Lexing- ton | Louis- ville | Baton Rouge | Lake Charles | New Orleans | Shreve- port | Lewis- ton | Portland | Balti- more | Boston | Brockton | Fall River | Law- rence | Lowell | New Bedford | Pitts- field | Spring- field | Wor- cester | Ann Arbor | Dear- born | Detroit | Flint | Grand Rapids | Kala- mazoo | Lansing | Sagi- naw | Duluth | Minne- apolis | Roches- ter | Biloxi | Jackson | Kansas City | St. Joseph | St. Louis | Spring- field | Billings | Great Falls | Lincoln | Omaha | Las Vegas | Reno | Man- chester | Nashua | Camden | Jersey City | Newark | Pater- son | Trenton | Albu- Querque | Albany | Binghamton | Buffalo | New York | Rochester | Schenectady | Syracuse | Utica | Yonkers | Charlotte | Durham | Greens- boro | Raleigh | Winston-Salem | Fargo | Akron | Canton | Cincinati | Cleveland | Columbus | Dayton | Lorain | Spring- field | Toledo | Youngs- town | Lawton | Oklahoma City | Tulsa | Eugene | Port- land | Allen- town | Erie | Harrisburg | Philadel- phia | Pittsburgh | Reading | Scranton | Provid- ence | Charleston | Columbia | Rapid City | Sioux Falls | Chattan- ooga | Knoxville | Memphis | Nashville | Abilene | Amarillo | Austin | Beaumont | Corpus Christi | Dallas | El Paso | Fort Worth | Houston | Lubbock | Odessa | San Antonio | Waco | Wichita Falls | Ogden | Salt Lake City | Burlington | Rutland | Alex- andria | Newport News | Norfolk | Williamsburg (DEB Composite of Richmond and Newport News) | Fredericksburg (DEB Composite of Richmond and Alexandria) | Richmond | Roanoke | Seattle | Spokane | Tacoma | Charles- ton | Hunting- ton | Green Bay | Kenosha | Madison | Milwau- kee | Racine | Cheyenne | Calgary | Edmonton | Hamilton | London | Montreal | Ottawa | Quebec | Toronto | Van- couver | Winnipeg
2024 | 256.5 | 253.1 | 250.9 | 255 | 252 | 344.3 | 252.7 | 248 | 234.6 | 241.1 | 314 | 318.9 | 321.1 | 314.7 | 317.6 | 315.6 | 311.8 | 306.2 | 354.8 | 313 | 321.8 | 319.8 | 247.9 | 260.1 | 253.8 | 307.2 | 306.6 | 311.3 | 305.6 | 307 | 306.4 | 307.1 | 306.3 | 306.5 | 286.3 | 249.1 | 246.4 | 253.4 | 251.7 | 249.8 | 251.6 | 259.8 | 260.4 | 263.2 | 257.7 | 262.1 | 361.5 | 265.9 | 266.2 | 344.7 | 290.8 | 337.9 | 294.2 | 314.9 | 294.7 | 260.2 | 264.8 | 264.5 | 297 | 265.6 | 260 | 274.5 | 262.6 | 266.9 | 273.4 | 278.7 | 260.6 | 263.7 | 263.7 | 258.8 | 266.8 | 266.6 | 255.3 | 250.9 | 255.4 | 255.1 | 273.8 | 286.7 | 278.9 | 323.1 | 311.5 | 306.8 | 327.3 | 320.1 | 305.7 | 294.8 | 298.8 | 307.9 | 290.3 | 293.9 | 294.3 | 280.4 | 286.9 | 275.2 | 287 | 275.8 | 299.8 | 313.1 | 295.4 | 246.3 | 254.4 | 291.8 | 275.5 | 288.1 | 260.4 | 263.5 | 259.5 | 266.8 | 273.4 | 307.8 | 288 | 288.7 | 287 | 329.1 | 321.7 | 330.1 | 322.1 | 331.7 | 258.9 | 299 | 289.5 | 301 | 374.3 | 294.7 | 292.9 | 289.2 | 286.8 | 343.4 | 257.9 | 246.7 | 243.3 | 241.4 | 242.8 | 258.8 | 266.3 | 264.5 | 261.2 | 269.1 | 265 | 256.5 | 259.5 | 253.2 | 270.1 | 257.7 | 256.1 | 258.4 | 245.5 | 284.8 | 289.2 | 290.4 | 274.9 | 294.3 | 331.8 | 299.2 | 287.6 | 281.8 | 304.9 | 255.2 | 259.4 | 249.2 | 266.8 | 260.3 | 254.2 | 267.3 | 267 | 243.3 | 248.2 | 252.3 | 242.8 | 249.7 | 239.5 | 246 | 244.1 | 248 | 245.5 | 244.2 | 247.3 | 241.1 | 239.4 | 251.9 | 259.3 | 273.4 | 266.4 | 279.3 | 256.6 | 261.9 | 257 | 268.35 | 257.4 | 262.2 | 298.9 | 275.9 | 295.1 | 275.6 | 278.7 | 287.5 | 294.8 | 298.1 | 289.3 | 291.6 | 262.4 | 319.8 | 318.4 | 311.9 | 315.2 | 291.2 | 305.3 | 290.6 | 311.5 | 310.2 | 294.3
2023 | 267.6 | 265.4 | 260.8 | 265.1 | 263.5 | 352.5 | 281.3 | 271.1 | 250.5 | 255.9 | 331.2 | 335.3 | 339.6 | 346.9 | 333.4 | 331.4 | 340 | 338.4 | 386.1 | 330.8 | 340.7 | 348.2 | 266.9 | 279.5 | 270.7 | 317.5 | 317.3 | 321.2 | 315.9 | 317.1 | 316.5 | 317.2 | 317 | 310.3 | 289.1 | 262.7 | 261.8 | 268 | 270.4 | 263.8 | 265.8 | 266.8 | 275.4 | 267.8 | 266.4 | 270.6 | 355.5 | 283.8 | 282 | 344.1 | 294.8 | 336.1 | 296.2 | 317.5 | 298.5 | 262.8 | 269.4 | 262.5 | 290.2 | 275.1 | 264.6 | 275.5 | 269.6 | 273.1 | 280.6 | 285.1 | 265.2 | 267.7 | 259.7 | 254.8 | 263.4 | 269.6 | 260.9 | 253.7 | 265.3 | 261.5 | 277 | 284.1 | 284.3 | 337.7 | 307.1 | 305.6 | 315.6 | 316.1 | 304.7 | 293.4 | 301.6 | 309.1 | 280 | 284.2 | 287.7 | 271.3 | 274.8 | 270 | 276.5 | 265.9 | 297.4 | 313.7 | 294.6 | 251.9 | 259.6 | 292.4 | 272.1 | 290.3 | 265.2 | 276.5 | 274.1 | 264 | 268.4 | 318.9 | 288 | 291.1 | 287.8 | 329.7 | 330.4 | 338.8 | 334.8 | 333.3 | 269 | 306.8 | 290.9 | 310.1 | 374.1 | 298.5 | 306 | 294.2 | 290.6 | 343 | 262.3 | 262.3 | 259.2 | 285.1 | 258.6 | 267.9 | 280.3 | 272.2 | 273.9 | 288.6 | 282.1 | 268.6 | 275.7 | 269 | 283.7 | 274 | 256.1 | 259.4 | 255.2 | 300.4 | 306.4 | 295 | 278.1 | 287.7 | 339.8 | 300.2 | 292.6 | 287 | 316.8 | 264.3 | 258.8 | 256.5 | 276.9 | 252 | 247.2 | 259 | 258.7 | 250.1 | 254.6 | 254.9 | 254.5 | 254.5 | 261.8 | 252.4 | 258.3 | 261 | 252.5 | 250.2 | 254.4 | 252.2 | 251.3 | 268.8 | 278 | 282.9 | 275.9 | 275.9 | 256.8 | 258.5 | 258.1 | 269.35 | 262.8 | 260.8 | 324 | 286.4 | 316.3 | 282 | 281.5 | 294.5 | 297 | 296.3 | 306.6 | 295.6 | 269.6 | 342.8 | 360.2 | 361.8 | 352.7 | 343.4 | 352.6 | 344.3 | 359.4 | 353.4 | 337.2
2022 | 245.3 | 243.5 | 239.8 | 243.3 | 242.2 | 316.4 | 250.3 | 240.1 | 226.3 | 228.7 | 305.3 | 305.8 | 309.7 | 315.9 | 304.5 | 304.6 | 309.2 | 307.4 | 353.9 | 302.8 | 314 | 319.9 | 243.3 | 254.9 | 244.7 | 290.5 | 290.1 | 293.2 | 288.8 | 291.1 | 290 | 290.6 | 290.2 | 286.7 | 268.5 | 238.6 | 236.5 | 243.4 | 241.7 | 240.4 | 243.1 | 241.4 | 249.2 | 243 | 240.1 | 244.8 | 324.9 | 254.4 | 255.6 | 324.3 | 281.8 | 318.2 | 281.3 | 301.1 | 284.9 | 244.5 | 249.7 | 245.8 | 272.3 | 256.3 | 243 | 254.2 | 246.1 | 254.3 | 262.7 | 258.8 | 247.2 | 242.1 | 246.6 | 238.1 | 239.9 | 246 | 233.7 | 229.6 | 241.1 | 232.8 | 256.2 | 262.2 | 261.4 | 314.2 | 286 | 283.6 | 294.2 | 294.5 | 283.5 | 272.2 | 279.9 | 288 | 267.7 | 271.5 | 277.7 | 258.6 | 251.2 | 247.7 | 260.5 | 253.4 | 286.8 | 297.6 | 281.9 | 232.8 | 236.9 | 275.3 | 257.7 | 276 | 251.2 | 256.2 | 255.6 | 247.6 | 250.2 | 289.7 | 261.8 | 266.9 | 264.7 | 309.3 | 308.4 | 316 | 310.3 | 311.8 | 241.4 | 283.1 | 271.1 | 289 | 351.2 | 279.1 | 282 | 273.3 | 271.1 | 320.5 | 242.1 | 241.7 | 238.1 | 236.8 | 237.5 | 249.7 | 256.7 | 248.9 | 249.1 | 263.8 | 254.6 | 242.3 | 250.9 | 243.7 | 259.3 | 251.3 | 236.4 | 237.4 | 230.8 | 284.5 | 288.5 | 276.6 | 259.1 | 271.2 | 316 | 279.4 | 271.8 | 267.4 | 290.3 | 241.8 | 238.7 | 239.1 | 253.2 | 237.9 | 233.2 | 244.1 | 247.8 | 230.5 | 232.5 | 231.2 | 230.9 | 232.3 | 242.3 | 234.5 | 234.4 | 238.7 | 234.4 | 231.6 | 233.4 | 228.8 | 227.7 | 243.8 | 251.2 | 257.2 | 251.4 | 256.2 | 239.3 | 242.6 | 240.5 | 248.95 | 241.7 | 241.3 | 295.1 | 259.9 | 288.2 | 259.5 | zxc | 274.7 | 276.3 | 276.7 | 279.7 | 274.9 | 245.3 | 319.5 | 321.6 | 305.8 | 304.4 | 299.4 | 293.2 | 299.7 | 314.6 | 306 | 287.5
2021 | 204.8 | 202.8 | 202 | 205.5 | 202.6 | 272.2 | 208.2 | 203.9 | 191.8 | 193.6 | 263 | 261 | 265.9 | 267.3 | 261.1 | 262.9 | 272.7 | 261.9 | 311.7 | 259.3 | 271.6 | 282.5 | 210.4 | 218.2 | 208.1 | 253.7 | 252.8 | 256.6 | 252.2 | 254.8 | 253.1 | 260.5 | 253.6 | 245.4 | 227.7 | 202.9 | 199 | 200.6 | 198.9 | 200.2 | 200 | 203.1 | 211.6 | 204.2 | 203.6 | 205.1 | 280.4 | 216.8 | 216.2 | 286.4 | 241.6 | 282.3 | 245.2 | 264.5 | 243.7 | 211.7 | 213.4 | 208 | 239.5 | 220.3 | 209.9 | 218.4 | 214.2 | 219.6 | 228.4 | 221.9 | 212.8 | 209.1 | 210.8 | 202.9 | 206.5 | 208.3 | 199.1 | 197 | 202.4 | 198.8 | 220 | 225.8 | 223.8 | 271.9 | 252.3 | 250 | 260 | 260.3 | 249.8 | 238.8 | 245.3 | 253.2 | 232.8 | 236.7 | 239 | 222.4 | 216.3 | 212.4 | 224.6 | 218 | 242.5 | 256.8 | 240.5 | 197.7 | 200.9 | 236.9 | 223.7 | 241 | 212.4 | 214.4 | 216.3 | 214.8 | 216.7 | 248.6 | 224.9 | 229.1 | 226.7 | 271.7 | 272 | 278.4 | 274.7 | 273.1 | 205 | 245 | 235 | 248.1 | 313 | 238.9 | 243.7 | 236.2 | 234.4 | 286.2 | 204.8 | 203.9 | 201.9 | 200.9 | 201.6 | 213.4 | 223.2 | 216.6 | 214.4 | 227.9 | 221.3 | 211.2 | 218.5 | 212.5 | 226.6 | 219.3 | 200.4 | 201.4 | 197.4 | 241.5 | 243.1 | 242.9 | 225.1 | 230.6 | 275.3 | 239.3 | 236.7 | 232.6 | 250.7 | 201.3 | 200.4 | 204 | 215.9 | 202.8 | 195.5 | 205.2 | 210.8 | 195.4 | 196.7 | 195.7 | 198.7 | 200.1 | 203.2 | 196.2 | 197.6 | 204.8 | 196.3 | 194.4 | 199.5 | 192.6 | 192.8 | 207.3 | 213.2 | 221.3 | 215.8 | 220.5 | 203.7 | 204.5 | 206.45 | 214.85 | 209.2 | 205 | 256.4 | 225 | 249.6 | 222.7 | 224.6 | 237.9 | 241.1 | 240.3 | 244.5 | 240.1 | 209.4 | 257.9 | 260.8 | 255.1 | 253.8 | 254.8 | 255.6 | 255.4 | 260.9 | 256.6 | 237.7
2020 | 201.7 | 201.1 | 200.1 | 202.5 | 200.2 | 272.3 | 205.3 | 200.3 | 187.6 | 191.5 | 260.3 | 256.9 | 263.1 | 262.9 | 258.6 | 260.2 | 269.5 | 256.9 | 305.7 | 257.6 | 267.8 | 276 | 208 | 213.5 | 206.3 | 249.9 | 248 | 250.9 | 247.4 | 250.2 | 249.4 | 255.9 | 249.1 | 239.4 | 223.8 | 195.3 | 197.6 | 199.2 | 197 | 197.6 | 199.2 | 200.5 | 205.6 | 201.8 | 200.1 | 203.2 | 278.4 | 215.4 | 214.5 | 282.7 | 238.5 | 269.1 | 237.9 | 253 | 242.2 | 208.9 | 210.6 | 206.3 | 238.6 | 217.7 | 207.2 | 214.5 | 210.7 | 217.6 | 227.3 | 218.8 | 211.5 | 205.2 | 207.2 | 202.8 | 203.1 | 206 | 197.9 | 196 | 200.9 | 196 | 217.8 | 221.4 | 220.8 | 266 | 248.6 | 247.2 | 256.6 | 254.8 | 246 | 232.7 | 239.3 | 248 | 228.1 | 228.9 | 234.7 | 216.6 | 211.7 | 207.1 | 217.1 | 212.8 | 238.5 | 252.1 | 234.8 | 193.9 | 197.1 | 233.7 | 218.8 | 234.4 | 208.3 | 214.4 | 213.5 | 213.2 | 213.8 | 245.4 | 225.5 | 226.8 | 224.8 | 268.3 | 265.9 | 273 | 269.1 | 262.2 | 204.9 | 239.9 | 232 | 245.1 | 306 | 237.4 | 239.6 | 233.3 | 231.7 | 281.2 | 203.6 | 201.3 | 199.3 | 198 | 199 | 213.1 | 218.7 | 212 | 211.6 | 225.6 | 218.4 | 208.3 | 216 | 208.7 | 222.7 | 214.2 | 195.3 | 197.2 | 193.6 | 235.2 | 240.1 | 240.1 | 221.9 | 229.6 | 268.8 | 234.6 | 236.2 | 229.7 | 248.8 | 200.6 | 199.9 | 204 | 210.3 | 200.4 | 191.3 | 203.3 | 209.2 | 192.6 | 193.7 | 191.3 | 195.8 | 193.7 | 199.5 | 194.1 | 194.4 | 202.2 | 195.5 | 193.4 | 195.5 | 189.3 | 190.6 | 205.6 | 211.8 | 220.1 | 215.3 | 217.6 | 202.3 | 204.3 | 205.25 | 212.9 | 208.2 | 202.9 | 252.3 | 216.5 | 240.4 | 221.9 | 222 | 232.2 | 237.7 | 233.8 | 240.5 | 238.5 | 207 | 256 | 259.4 | 254.4 | 252.2 | 249.7 | 254.1 | 249.8 | 259.5 | 250.9 | 235.6
2019 | 190 | 189.2 | 186.5 | 188.7 | 189.8 | 258.5 | 196.1 | 191.3 | 180.4 | 183.6 | 247.3 | 244.6 | 248.1 | 252.3 | 244.9 | 246.7 | 253.7 | 245.8 | 286.7 | 243.9 | 252 | 259.7 | 197.1 | 201.4 | 196.7 | 237 | 236.5 | 237.4 | 236 | 238.3 | 236.7 | 243.3 | 237.1 | 229.9 | 211.2 | 182.8 | 182.6 | 183.6 | 186 | 184.5 | 186.2 | 190.2 | 196 | 190.5 | 190.3 | 191.7 | 266.9 | 203.9 | 204.5 | 266.1 | 226.3 | 262.3 | 232.2 | 247.7 | 227.9 | 199.8 | 202.4 | 196.8 | 227.3 | 203.6 | 198.9 | 203.6 | 202.4 | 206.9 | 216.6 | 205.7 | 199.6 | 198.8 | 198.7 | 192.6 | 195.3 | 194.4 | 188.2 | 187.5 | 189.8 | 186.5 | 201.1 | 203.7 | 208.7 | 253.2 | 237.2 | 235 | 243.7 | 242.3 | 234.5 | 222.9 | 225.6 | 237 | 219.7 | 220.7 | 223.8 | 208.7 | 201.3 | 198.5 | 208.3 | 204.9 | 223.8 | 237.1 | 220.2 | 183.6 | 184.4 | 224.8 | 212.8 | 227.1 | 203 | 199.8 | 200.3 | 199.5 | 200.1 | 232.4 | 211 | 211 | 210.2 | 248 | 251.7 | 256.3 | 254.7 | 250.5 | 195.8 | 226.3 | 219.5 | 234 | 296.1 | 223.6 | 226.6 | 219.6 | 215.8 | 268.4 | 187.3 | 191.1 | 189.1 | 186.8 | 188.6 | 203.4 | 210.3 | 203.3 | 199.4 | 213.8 | 203.2 | 194.7 | 207.1 | 196.8 | 212.5 | 204.6 | 187.4 | 186.2 | 184.8 | 219.1 | 221.7 | 226.1 | 209.9 | 213.7 | 253.5 | 224.9 | 221 | 217.7 | 232.7 | 189.1 | 187.4 | 196.5 | 200.8 | 191.3 | 182.8 | 191.3 | 190.9 | 182.1 | 181.4 | 182.3 | 186.2 | 184.5 | 188.6 | 181.9 | 183.9 | 188.7 | 184.7 | 183.6 | 184.5 | 180.1 | 179.7 | 194.3 | 199.5 | 203.9 | 200.4 | 206.2 | 189.6 | 190.3 | 193.55 | 201.85 | 197.5 | 194.5 | 235.3 | 209.2 | 228.6 | 211.8 | 215.7 | 218.3 | 226.2 | 221.1 | 228.3 | 226 | 197.8 | 244.2 | 245.2 | 230.9 | 239 | 237.4 | 241.2 | 236.1 | 246.1 | 234 | 221.8
2018 | 186.4 | 185.6 | 183 | 185.1 | 186.2 | 253.6 | 192.4 | 187.7 | 177 | 180.1 | 242.6 | 240 | 243.4 | 247.5 | 240.3 | 242.1 | 248.9 | 241.2 | 281.3 | 239.3 | 247.3 | 254.8 | 193.4 | 197.6 | 193 | 232.5 | 232 | 232.9 | 231.6 | 233.8 | 232.2 | 238.7 | 232.6 | 225.6 | 207.2 | 179.4 | 179.2 | 180.1 | 182.5 | 181 | 182.7 | 186.6 | 192.3 | 186.9 | 186.7 | 188.1 | 261.9 | 200.1 | 200.6 | 261.1 | 222 | 257.4 | 227.8 | 243 | 223.6 | 196 | 198.6 | 193.1 | 223 | 199.8 | 195.2 | 199.8 | 189.6 | 203 | 212.5 | 201.8 | 195.8 | 195.1 | 195 | 189 | 191.6 | 190.7 | 184.7 | 184 | 186.2 | 183 | 197.3 | 199.9 | 204.8 | 248.4 | 232.7 | 230.6 | 239.1 | 237.7 | 230.1 | 218.7 | 221.4 | 232.5 | 215.6 | 216.5 | 219.6 | 204.8 | 197.5 | 194.8 | 204.4 | 201 | 219.6 | 232.6 | 216.1 | 180.1 | 180.9 | 220.6 | 208.8 | 222.8 | 199.2 | 196 | 196.5 | 195.7 | 196.3 | 228 | 207 | 207 | 206.2 | 243.3 | 247 | 251.5 | 249.9 | 245.8 | 192.1 | 222 | 215.4 | 229.6 | 290.5 | 219.4 | 222 | 215.5 | 211.7 | 263.3 | 183.8 | 187.5 | 185.5 | 183.3 | 185 | 199.6 | 206.3 | 199.5 | 195.6 | 209.8 | 199.4 | 191 | 203.2 | 193.1 | 208.5 | 200.7 | 183.9 | 182.7 | 181.3 | 215 | 217.5 | 221.8 | 205.9 | 209.7 | 248.7 | 220.7 | 216.8 | 213.6 | 228.3 | 185.5 | 183.9 | 192.8 | 197 | 187.7 | 179.4 | 187.7 | 187.3 | 178.7 | 178 | 178.9 | 182.7 | 181 | 185 | 178.5 | 180.4 | 185.1 | 181.2 | 180.1 | 181 | 176.7 | 176.3 | 190.6 | 195.7 | 200.1 | 196.6 | 202.3 | 186 | 186.7 | 189.9 | 198.05 | 193.8 | 190.8 | 230.9 | 205.3 | 224.3 | 207.8 | 211.6 | 214.2 | 221.9 | 216.9 | 224 | 221.7 | 194.1 | 239.6 | 240.6 | 226.6 | 234.5 | 232.9 | 236.7 | 231.7 | 241.5 | 229.6 | 217.6
2017 | 178.6 | 178.3 | 177.9 | 178.5 | 179.6 | 246.2 | 183.8 | 181.3 | 170.6 | 172.8 | 233.6 | 229.2 | 232 | 237.8 | 231.9 | 233.2 | 237.9 | 229.3 | 270.8 | 231.1 | 236.2 | 246.8 | 187.3 | 187.8 | 183.1 | 224.4 | 222.9 | 223.9 | 222.5 | 225 | 224.2 | 230.8 | 224.2 | 217.7 | 199.1 | 173.7 | 172.7 | 173.4 | 176.5 | 174.1 | 177 | 179.4 | 185.1 | 180.1 | 179.4 | 180.5 | 249.7 | 192.5 | 193.4 | 251.7 | 215.3 | 247.9 | 220.4 | 233.1 | 216 | 189.8 | 192.3 | 185.2 | 216.8 | 191.8 | 189.5 | 192.4 | 193.1 | 194.8 | 205.7 | 195 | 188.2 | 188.5 | 188.1 | 183 | 186.2 | 185 | 179.2 | 178.2 | 179.3 | 177.9 | 192 | 194.7 | 197.7 | 240 | 226.4 | 225 | 233.9 | 231.3 | 224.4 | 211.7 | 213.5 | 226.1 | 208.7 | 211.1 | 212.1 | 199.2 | 190.9 | 189.6 | 198.1 | 195.3 | 212.1 | 221.2 | 207.6 | 175.3 | 175.6 | 212.9 | 202.8 | 213.1 | 192.9 | 190.4 | 191 | 189.6 | 190.1 | 220.1 | 199.8 | 200.7 | 200 | 236.3 | 238.7 | 242.7 | 240.8 | 239.2 | 185.9 | 213.5 | 208.4 | 220.8 | 282.9 | 213 | 213.8 | 208.9 | 205.9 | 256.8 | 177 | 180.3 | 178.2 | 175.8 | 178 | 182.8 | 199.4 | 192.2 | 186.1 | 202.6 | 191.6 | 186.1 | 196.9 | 187.8 | 201.4 | 194.2 | 178 | 177 | 174.8 | 207.3 | 209.5 | 213.7 | 199.5 | 202.4 | 239.8 | 213.6 | 210.7 | 207.4 | 218.6 | 178.4 | 176.5 | 185.3 | 184.8 | 181.9 | 173.3 | 180.9 | 180.5 | 174 | 172.8 | 172.6 | 178 | 178.9 | 180 | 173.5 | 174.9 | 179.2 | 176.6 | 175.6 | 175.5 | 170.7 | 170.4 | 183.3 | 188.8 | 192.8 | 189.5 | 195.6 | 180.7 | 180.5 | 181.75 | 189.2 | 182.8 | 185.1 | 219.3 | 198.8 | 215.8 | 201.5 | 204.5 | 206.9 | 213.6 | 207.4 | 215.2 | 213.8 | 185 | 231.4 | 232.3 | 227.8 | 225 | 221.8 | 227.7 | 222.9 | 231.4 | 221.5 | 207.7
2016 | 185.6 | 184.2 | 184.1 | 183.5 | 186.3 | 246.3 | 181.7 | 178.1 | 169.8 | 174.6 | 223.6 | 221.3 | 224.3 | 226.2 | 222.5 | 223.3 | 227.3 | 218.3 | 256.6 | 221.9 | 227.9 | 236 | 189.4 | 191 | 186.2 | 226.4 | 225.6 | 226.1 | 225 | 226.9 | 232.7 | 233.3 | 225.7 | 215.7 | 201.3 | 177.7 | 176.3 | 179.1 | 180.4 | 173.4 | 180.6 | 176.3 | 185 | 173.6 | 172.4 | 175.1 | 251.7 | 191.1 | 190.2 | 244.9 | 212.9 | 244.3 | 217.5 | 229.6 | 215.1 | 190.5 | 192.3 | 184.4 | 216.8 | 192.5 | 191 | 190.7 | 192.8 | 191.4 | 199.9 | 190 | 184 | 181 | 181 | 191 | 186 | 188.1 | 180.1 | 176.7 | 180 | 173.2 | 197.2 | 200 | 193.8 | 245 | 230.5 | 229 | 236.9 | 235.5 | 228.2 | 216.1 | 218.3 | 230.1 | 211.3 | 212.5 | 212.8 | 200.2 | 191 | 189.7 | 200.9 | 195..9 | 217.6 | 227.2 | 212.4 | 173.3 | 177.7 | 213.2 | 205.5 | 212.1 | 194.6 | 191.8 | 191.1 | 186.8 | 187.6 | 221.1 | 198.8 | 200.9 | 200.5 | 228.8 | 229.6 | 232.9 | 231.3 | 229.3 | 181.6 | 209.6 | 202.6 | 213.7 | 270.5 | 208.4 | 209.8 | 203.6 | 200.8 | 247.9 | 180.6 | 182 | 179.8 | 174.6 | 179.6 | 185.5 | 202.4 | 195 | 190.1 | 205.9 | 195.2 | 189.3 | 199.9 | 190.6 | 206.1 | 197.9 | 177.7 | 180.1 | 172 | 209.1 | 209.2 | 214.8 | 199.7 | 202.4 | 238.2 | 212.2 | 207.6 | 207 | 221.6 | 176.8 | 176.6 | 174.7 | 175.2 | 177.4 | 173.9 | 181.9 | 181.8 | 173.7 | 171 | 173.3 | 178.3 | 175.5 | 177.9 | 172.8 | 174.1 | 180.5 | 175.2 | 172.6 | 173.1 | 170.3 | 170.1 | 179.4 | 184.7 | 193.6 | 190.2 | 195.6 | 178.3 | 178.2 | 178.6 | 187.25 | 178.9 | 178 | 213.4 | 195.1 | 209.7 | 204.2 | 206.5 | 207.4 | 212.8 | 207.4 | 214.4 | 212.4 | 178.6 | 229.1 | 229.4 | 221.7 | 221.3 | 218.5 | 223.4 | 218.9 | 228.6 | 219.3 | 205.3
2015 | 184.8 | 182.1 | 185.4 | 182.7 | 184.5 | 244.7 | 181 | 177.9 | 167.6 | 171.1 | 217.3 | 214.6 | 218.8 | 218.5 | 215.7 | 217.1 | 221 | 213.1 | 250.2 | 215.7 | 222.8 | 230.2 | 185.1 | 186.6 | 183.5 | 224.1 | 223.3 | 224.2 | 222.8 | 225 | 230.2 | 230.3 | 223.8 | 211.7 | 197.3 | 176.1 | 174.2 | 178.1 | 178.3 | 172.5 | 178.9 | 168.6 | 178.3 | 171.3 | 170 | 170.5 | 250.5 | 185.4 | 185.3 | 238.9 | 209 | 238.7 | 213.7 | 225.3 | 210.5 | 186.4 | 190.1 | 183 | 212.4 | 189.6 | 186 | 188.6 | 190.6 | 188.8 | 196.9 | 189 | 179.1 | 177.8 | 175.7 | 175.1 | 184.4 | 185.9 | 176.6 | 175.4 | 177.6 | 170.9 | 193.7 | 196.9 | 189.2 | 240.7 | 228.3 | 228.2 | 234.5 | 233.2 | 227.4 | 212.8 | 214.6 | 226.8 | 209.8 | 211.5 | 211.8 | 198.9 | 191.2 | 190.4 | 199.6 | 194.1 | 212.9 | 222 | 209.1 | 167.3 | 174.2 | 210 | 202.3 | 210.1 | 191.8 | 188.1 | 188.4 | 183.7 | 184.7 | 215.5 | 194.9 | 198.7 | 197.8 | 224.5 | 226.1 | 230.1 | 228.5 | 227.6 | 178.3 | 208.1 | 202.4 | 209.6 | 268 | 203.5 | 207.4 | 200.9 | 198.1 | 243.4 | 173.1 | 172.3 | 170.5 | 167.6 | 170.6 | 181 | 199.1 | 191.1 | 188.1 | 203.4 | 192.4 | 187.9 | 196.7 | 188.1 | 201 | 193.3 | 175.1 | 177.1 | 170 | 203.1 | 204.3 | 209.8 | 194.5 | 200.3 | 234.7 | 209.5 | 204.2 | 201.7 | 219.9 | 171.3 | 171.9 | 167.7 | 168 | 174.3 | 171 | 177.5 | 179.9 | 170.8 | 170.7 | 172.3 | 174 | 172.8 | 174.4 | 168.8 | 172.5 | 176.4 | 173.3 | 171.5 | 171.8 | 167.3 | 169 | 177.1 | 182.1 | 191.6 | 188.5 | 192.5 | 175.8 | 177.4 | 176.5 | 184.85 | 177.2 | 175.3 | 209.9 | 193.1 | 207.2 | 199.9 | 201.3 | 200.8 | 205.4 | 202 | 209.4 | 205.1 | 175.4 | 226.6 | 226.3 | 221.2 | 217 | 220.4 | 220.4 | 220.4 | 225.9 | 217.1 | 204.1
2014 | 180.3 | 175.8 | 170.6 | 163.1 | 165.9 | 241 | 180 | 177 | 165.1 | 168.4 | 214.2 | 215.2 | 217 | 217.3 | 214.8 | 214.1 | 221.5 | 211.4 | 248 | 214.7 | 218.4 | 227.9 | 187.8 | 189.1 | 184.7 | 223.8 | 222.8 | 223.9 | 222.4 | 224.1 | 230.3 | 230.5 | 223.2 | 210.2 | 197 | 176.5 | 171 | 178.4 | 176.5 | 164.4 | 183.2 | 166.6 | 177.5 | 170.2 | 168.2 | 167.2 | 239.7 | 184.1 | 184.4 | 238.1 | 206 | 236.8 | 212.5 | 224.4 | 208.2 | 184.5 | 188.1 | 180.8 | 210.1 | 188.4 | 185 | 185.5 | 189.2 | 188.3 | 195.9 | 188.5 | 178.9 | 177.4 | 173.6 | 173.7 | 183.7 | 186.1 | 171.3 | 170.9 | 177.5 | 167.7 | 192.4 | 195.4 | 187.6 | 239.1 | 229.1 | 229.3 | 234.8 | 233.9 | 228.5 | 213.3 | 214.8 | 227.3 | 206.1 | 208.4 | 208.7 | 196 | 187.9 | 188.4 | 195.7 | 191.7 | 211.1 | 220.7 | 207.5 | 164.6 | 169.8 | 210.8 | 199.3 | 208.6 | 189.5 | 185.4 | 186.3 | 181.1 | 183.7 | 210.9 | 195.7 | 198.8 | 197.3 | 224.6 | 226.6 | 230.6 | 227.8 | 226.6 | 178 | 205.1 | 202.4 | 207.8 | 267.7 | 202.2 | 204.2 | 198.8 | 196.4 | 245.6 | 165.5 | 165.2 | 163.9 | 161.6 | 164.3 | 177.1 | 199.2 | 190.8 | 188.1 | 203.1 | 192.4 | 185.8 | 196.7 | 187.2 | 199.7 | 193.8 | 169.3 | 170.9 | 166.7 | 200.4 | 201.4 | 209 | 191.4 | 200.3 | 232.1 | 207.1 | 201.4 | 201.4 | 220.3 | 171 | 162.5 | 168.6 | 166.8 | 174.1 | 170.9 | 176.5 | 178.2 | 160.9 | 167.2 | 167.5 | 165.2 | 167.3 | 172.4 | 156.2 | 169.5 | 176 | 166.9 | 159.2 | 169.5 | 161.7 | 160.6 | 174.2 | 177.1 | 191.3 | 188.6 | 190.5 | 174.4 | 175.7 | 175.4 | 183.45 | 176.4 | 173.5 | 209.8 | 190.8 | 205.2 | 197 | 199.5 | 198.9 | 205.2 | 202.4 | 210.2 | 205.3 | 173.6 | 228.2 | 229.1 | 222.1 | 218.9 | 219.8 | 214.8 | 218.3 | 227.4 | 218.8 | 202.9
2013 | 173.3 | 168.7 | 165.7 | 158.7 | 161.6 | 235.3 | 174.1 | 169.2 | 161.2 | 163.2 | 207 | 205.6 | 210.3 | 210.7 | 207.8 | 207 | 215 | 203.2 | 241 | 207.9 | 211.8 | 222.2 | 180.7 | 183.4 | 180 | 217.8 | 217.2 | 218.4 | 216.8 | 218.5 | 223.1 | 224.2 | 217.3 | 203.6 | 191.7 | 173.2 | 168.4 | 175.8 | 174.8 | 160.8 | 180.2 | 163.2 | 173.3 | 166.7 | 164.9 | 163.5 | 231.5 | 179.6 | 179.9 | 231.1 | 200.8 | 228.7 | 207.2 | 217.2 | 203.2 | 177.8 | 182.5 | 175.9 | 203.6 | 182.7 | 179.3 | 179.3 | 182.6 | 183.4 | 190.8 | 181.8 | 173.2 | 171.3 | 168.8 | 167.3 | 179.1 | 182.4 | 166.3 | 166.2 | 173.1 | 159 | 187.9 | 189.5 | 183.2 | 232.9 | 221.6 | 221.8 | 225.3 | 223.4 | 221.1 | 205.9 | 206.5 | 219.3 | 201.2 | 202.4 | 203.1 | 190.6 | 182.4 | 182.4 | 190.2 | 186.5 | 205.1 | 216.3 | 201.4 | 160.9 | 164.3 | 204.7 | 193.1 | 202.4 | 181.6 | 180.5 | 181.1 | 175.5 | 180.6 | 206.8 | 190.4 | 193.8 | 192.5 | 217.7 | 219.3 | 223.6 | 221.2 | 218.7 | 173.6 | 195.3 | 195.5 | 200.7 | 259.4 | 194.3 | 195.5 | 193.6 | 188.5 | 230 | 159.6 | 158.4 | 158.7 | 157.5 | 159.1 | 169.6 | 191.8 | 183.9 | 181.9 | 195.5 | 187.1 | 180.7 | 187.6 | 181.5 | 193.5 | 186.5 | 162.7 | 165.5 | 161.7 | 194.7 | 195.6 | 203.2 | 187.2 | 192.5 | 223.6 | 201.4 | 196.1 | 196 | 213.4 | 166.3 | 157.9 | 159.6 | 161.2 | 167.4 | 159.3 | 169.3 | 172.8 | 155.2 | 161.7 | 158.7 | 160.2 | 157.7 | 167.4 | 151.2 | 161.7 | 169.4 | 159.3 | 151.5 | 164.3 | 156.1 | 155.9 | 167.7 | 171.1 | 178.7 | 176.6 | 185 | 170 | 171.5 | 170.35 | 177.85 | 170.7 | 168.3 | 203.4 | 184.3 | 199.1 | 187.2 | 193.2 | 193.9 | 201.2 | 197.8 | 204.6 | 200.5 | 167.6 | 222.7 | 223.3 | 216 | 213.7 | 214.5 | 214.1 | 212.6 | 220.9 | 216.2 | 200.2
2012 | 169.1 | 162.7 | 163.2 | 153.8 | 154.6 | 232.5 | 172.2 | 166.4 | 158.7 | 161 | 204.1 | 202.9 | 207.3 | 207.2 | 204.7 | 204.1 | 211.9 | 198.9 | 237.6 | 204.8 | 208.8 | 218.9 | 179.4 | 182.2 | 177.9 | 213.9 | 213.3 | 214.4 | 212.9 | 214.7 | 219.8 | 220 | 213.4 | 201 | 189.6 | 170.9 | 165.8 | 173.7 | 172.8 | 158.5 | 177.8 | 158.3 | 170.7 | 160.6 | 159.3 | 158.9 | 227.9 | 170.4 | 171.5 | 226.2 | 195.7 | 222.7 | 199.7 | 211.8 | 197.2 | 175.2 | 177.8 | 171.8 | 197.9 | 180.6 | 175.8 | 174.3 | 178.9 | 180.3 | 184.6 | 179.2 | 168.8 | 169.2 | 162.3 | 161.4 | 174.8 | 177.5 | 164.4 | 163.8 | 171.7 | 153.2 | 180.7 | 182.4 | 180.8 | 229.3 | 217.2 | 217.8 | 221.6 | 219.3 | 217 | 200.2 | 201.9 | 215.2 | 196.1 | 199.2 | 200.2 | 186.3 | 176.4 | 178.9 | 185.9 | 182.8 | 203.1 | 214.7 | 199.7 | 157.6 | 160.5 | 200.8 | 189 | 198 | 177.7 | 178.6 | 179.5 | 169.3 | 177.1 | 202.6 | 186.8 | 189.2 | 188.3 | 213.6 | 215.2 | 219.2 | 217.5 | 213.7 | 171 | 191.2 | 192.9 | 198.1 | 256.3 | 191.2 | 191.4 | 189.6 | 185.2 | 227.1 | 156.4 | 155.6 | 156.3 | 155.4 | 157.2 | 167.3 | 187.7 | 180.2 | 178.6 | 191.4 | 183.5 | 177.6 | 184.1 | 178 | 190.4 | 183.3 | 158.1 | 158 | 151.3 | 190.1 | 191.8 | 199.3 | 182 | 187.9 | 221.8 | 196.8 | 190.8 | 191.5 | 209.3 | 155.3 | 148.1 | 156.7 | 158.8 | 163.8 | 155.8 | 166.3 | 167.5 | 152.5 | 158.6 | 154.3 | 158.2 | 151.8 | 165.2 | 149.1 | 159.4 | 167.8 | 156.6 | 149.1 | 160.7 | 153.8 | 152.9 | 165.6 | 168.8 | 172.4 | 170.5 | 182.4 | 168.3 | 169.7 | 168.85 | 175.9 | 169.4 | 166.4 | 201.9 | 181.6 | 194.3 | 183.4 | 186.4 | 190 | 195.5 | 191.2 | 202.2 | 194.9 | 165 | 219.1 | 219.6 | 211.1 | 208.2 | 209.6 | 209.7 | 207.5 | 216.6 | 214 | 200.7
2011 | 163 | 156.3 | 156.9 | 147.6 | 148.3 | 225.1 | 163.8 | 159.5 | 152 | 154.1 | 196.1 | 194.6 | 199.8 | 199.2 | 197 | 195.8 | 203.1 | 192.3 | 227.9 | 196.2 | 201.3 | 210.3 | 171.7 | 174.1 | 170.7 | 205.2 | 204.2 | 205.1 | 203.9 | 205.8 | 211 | 211.2 | 204.6 | 193.3 | 182.3 | 164.4 | 159.4 | 167 | 166.1 | 151.7 | 171.4 | 151.8 | 164 | 154.3 | 152.7 | 151.7 | 219 | 162.8 | 163.6 | 217.6 | 187.9 | 216.8 | 193.4 | 205.8 | 189.4 | 168.4 | 169.7 | 165 | 191 | 173 | 169.2 | 168.1 | 171.3 | 173.8 | 178.1 | 172.7 | 162.3 | 162.8 | 156.3 | 155.3 | 167.8 | 170.8 | 156.9 | 156.5 | 162.1 | 146.7 | 167.4 | 169.1 | 173.6 | 219.3 | 208.2 | 206 | 211.6 | 210.1 | 205.2 | 191.2 | 194.5 | 206.6 | 186.7 | 189.4 | 190.3 | 178.5 | 169.9 | 171.9 | 178 | 174.6 | 195.7 | 208.1 | 193.8 | 151.4 | 154.3 | 191.1 | 178.8 | 190.6 | 168.3 | 168.8 | 170.8 | 162.8 | 169.6 | 195.7 | 179.8 | 176.8 | 176.1 | 205.5 | 207 | 210.3 | 209.2 | 206.4 | 163.3 | 180.9 | 176.1 | 188.1 | 245.6 | 181.9 | 181.5 | 180.8 | 173.5 | 218.9 | 142.6 | 143.8 | 142.2 | 142.8 | 140.9 | 160.3 | 180.8 | 172.1 | 171.3 | 184 | 175.7 | 168.4 | 176.8 | 168.4 | 183.1 | 176.5 | 151.7 | 151.6 | 144.8 | 184.9 | 186.6 | 192.2 | 176 | 180.9 | 212.8 | 187.7 | 184.3 | 185.3 | 196.8 | 149.4 | 142.3 | 149.5 | 151.3 | 157.3 | 149.3 | 158.4 | 160.7 | 145.9 | 151.9 | 147.6 | 152.4 | 145 | 157.9 | 142.5 | 152.8 | 160.8 | 150 | 142.5 | 152.6 | 147.3 | 146.6 | 158.7 | 161.8 | 158.8 | 157.1 | 174.5 | 159.8 | 161.1 | 159.4 | 166.75 | 159 | 154.2 | 194.1 | 175.5 | 187.6 | 177.5 | 180.3 | 181.4 | 187.6 | 183.4 | 191.9 | 187 | 155.3 | 212.6 | 212.4 | 204.2 | 200.1 | 202.1 | 202 | 200.6 | 209.6 | 207.1 | 192.6
2010 | 159.6 | 152.9 | 153.1 | 144.4 | 144.9 | 218.3 | 160.7 | 157.3 | 150.3 | 152.5 | 192.8 | 190.8 | 195 | 194.9 | 192.8 | 192.7 | 196.7 | 188.2 | 223 | 192.9 | 195.9 | 204.6 | 170.5 | 172.6 | 168.1 | 198.8 | 199.1 | 199.8 | 198.8 | 200.7 | 198.3 | 203.8 | 199.4 | 187.7 | 179 | 160.3 | 155.4 | 163.3 | 162.5 | 148.1 | 167.5 | 148.3 | 160.1 | 150.9 | 149.4 | 147.9 | 214.6 | 161.7 | 162.4 | 210.6 | 181.2 | 208.3 | 186.2 | 197.6 | 182.2 | 162.8 | 165.9 | 160 | 183.7 | 168.1 | 163.1 | 163.5 | 167.8 | 170.4 | 175.6 | 170.2 | 159 | 160.2 | 152.8 | 151.3 | 158.7 | 166.9 | 153.7 | 153.4 | 160.3 | 145.1 | 162.1 | 163.7 | 168.3 | 214.3 | 202.7 | 200.7 | 204.9 | 204.7 | 200 | 185.9 | 189.4 | 201.1 | 183.3 | 186.8 | 187.5 | 176.2 | 160.6 | 167.3 | 175.8 | 171.9 | 193.1 | 203.8 | 188.9 | 148 | 151 | 186.1 | 174.2 | 185.9 | 164.3 | 166.5 | 168.6 | 159.3 | 165.8 | 193.7 | 175.6 | 172.5 | 172 | 201.2 | 203.3 | 206.3 | 205.3 | 200.8 | 162.5 | 177.8 | 173.8 | 184 | 241.4 | 179.6 | 179 | 176.7 | 170.5 | 217.1 | 140.5 | 141.6 | 140 | 140.6 | 138.8 | 156.2 | 174.5 | 167.5 | 166.5 | 180.2 | 170.3 | 163.4 | 173 | 164.6 | 176.5 | 171.7 | 149.5 | 149.4 | 143.1 | 181.5 | 182.9 | 187.9 | 171 | 175.2 | 209.3 | 182.3 | 179.8 | 180.8 | 192.8 | 147.4 | 140.2 | 147.3 | 149 | 152.4 | 144.7 | 154.2 | 156.7 | 144.2 | 150.1 | 144.7 | 150.5 | 142.1 | 155.1 | 140.8 | 149.6 | 157.3 | 148.1 | 140.7 | 147.9 | 145.8 | 145 | 157.5 | 160.9 | 156.3 | 154.6 | 170.9 | 156.7 | 158 | 156.65 | 163.75 | 156.6 | 151.8 | 191.8 | 171.5 | 186 | 171.6 | 176.1 | 179 | 185.1 | 181.3 | 187.1 | 184.4 | 154.4 | 200.6 | 200.7 | 197.7 | 193.7 | 193.9 | 195.6 | 192.7 | 200.7 | 192.7 | 182.9
2009 | 162.7 | 157.2 | 155.6 | 148.8 | 149.4 | 222.9 | 161.3 | 156.8 | 149.2 | 156.3 | 194.5 | 192.3 | 195 | 196.6 | 194.5 | 193.1 | 198.1 | 191.6 | 224.9 | 193.6 | 194.5 | 202.7 | 168.4 | 172 | 166.7 | 199 | 197.7 | 198.7 | 197.4 | 199.3 | 198.8 | 204.3 | 198.4 | 188.9 | 181.4 | 160.7 | 152 | 165.2 | 163.9 | 145.1 | 165.1 | 152 | 164.5 | 155.6 | 153.5 | 152.8 | 218.6 | 162.6 | 163.4 | 209 | 182.2 | 205.9 | 186.2 | 196.5 | 184 | 164.9 | 166.9 | 163 | 185.2 | 170.3 | 164.5 | 167.1 | 168 | 165.9 | 172 | 162.1 | 156.3 | 147.6 | 154.5 | 152.4 | 160.7 | 167.5 | 156.9 | 154.4 | 161.9 | 147.6 | 159.4 | 161.8 | 169.1 | 211.8 | 199.2 | 197.6 | 201.9 | 201.9 | 196.9 | 185.1 | 187.1 | 198.2 | 179.2 | 186.9 | 187.8 | 176 | 156.7 | 166.3 | 173.7 | 168.6 | 191.8 | 203.1 | 188 | 152.8 | 156.6 | 185.6 | 172.3 | 187.2 | 163.7 | 165.3 | 166 | 161.7 | 165 | 191.5 | 176.5 | 174 | 173.5 | 196.8 | 200.5 | 203.6 | 202 | 198.6 | 163 | 178.1 | 172.9 | 184.4 | 239.9 | 179.6 | 178.8 | 176.9 | 171.3 | 217.5 | 145.1 | 145.8 | 144 | 145.1 | 142.7 | 154.3 | 175.7 | 168.4 | 168.1 | 181.6 | 171.2 | 165.3 | 174 | 166 | 178.5 | 172.8 | 152.5 | 153.3 | 146.8 | 181.3 | 183.6 | 188.3 | 171.9 | 176.5 | 209.5 | 181.7 | 180.7 | 181.3 | 192.9 | 150.8 | 144.3 | 148.2 | 151.1 | 155.7 | 148 | 157.2 | 159.8 | 143.5 | 147.3 | 146.4 | 149.8 | 141.7 | 155.5 | 141.1 | 150.1 | 160.9 | 144.6 | 139.1 | 150.8 | 146.7 | 146.1 | 155.1 | 160.4 | 158.3 | 156.7 | 172.5 | 160 | 161.9 | 160.35 | 166.6 | 160.7 | 155.6 | 188.5 | 173 | 186.3 | 174.6 | 177.4 | 175.5 | 182.5 | 180 | 187.3 | 182.8 | 155.2 | 205.4 | 206.6 | 203 | 198.9 | 198.8 | 200.1 | 197.4 | 205.6 | 199.6 | 188.5
2008 | 150.3 | 146.9 | 143.7 | 138.4 | 138.8 | 210.8 | 152.2 | 148.4 | 138.6 | 145.4 | 182.7 | 179.8 | 183.2 | 184.7 | 182.6 | 181.3 | 186 | 179.9 | 210.6 | 181.5 | 183.2 | 191.6 | 158.8 | 161.9 | 157.9 | 185.8 | 184.8 | 185.7 | 184.5 | 186.1 | 185.2 | 189.2 | 185.3 | 177.5 | 170.4 | 149.6 | 142.5 | 152.9 | 153 | 135.3 | 155.6 | 140.4 | 153.2 | 143.9 | 142.5 | 141.1 | 205.5 | 153.2 | 152.8 | 195.7 | 168.7 | 185.5 | 172.2 | 180.2 | 168.5 | 152.4 | 155.8 | 151 | 169 | 159.2 | 153 | 153.1 | 155.9 | 157.3 | 163.4 | 152.4 | 147.8 | 139.2 | 144.9 | 143.1 | 152 | 156.8 | 144 | 141.5 | 149.3 | 135.9 | 149.1 | 150.9 | 157.7 | 198.6 | 186.4 | 185.1 | 188.7 | 189.1 | 184.5 | 171.3 | 173.7 | 184.5 | 169.6 | 176.4 | 177 | 164.4 | 140.2 | 155.7 | 161.6 | 158.7 | 177.4 | 190.6 | 175 | 141.8 | 147.1 | 175.5 | 164.2 | 176.2 | 152.9 | 153.1 | 154.6 | 152 | 154.8 | 176.2 | 167 | 162.5 | 161.9 | 184 | 187.3 | 189.6 | 188.7 | 185.6 | 152.6 | 166 | 160.7 | 173.9 | 226.8 | 168 | 167.2 | 165.9 | 161.6 | 202.1 | 135.8 | 136.6 | 134.6 | 135.3 | 133.8 | 145 | 165.4 | 158.4 | 159 | 170.6 | 160.2 | 157.5 | 163.9 | 157.5 | 168.2 | 161.5 | 141.3 | 140.6 | 136.2 | 172.3 | 174.7 | 175.7 | 161 | 165.7 | 196.2 | 169.2 | 169.3 | 167.9 | 178.2 | 142.1 | 134.8 | 138.4 | 141.3 | 136.7 | 133.4 | 146 | 147.5 | 132.4 | 137 | 137.5 | 140.3 | 133.2 | 144.1 | 130.7 | 138.3 | 149.1 | 134.7 | 128.9 | 141 | 136.1 | 136.1 | 144.8 | 149.7 | 147.2 | 145.8 | 161.8 | 150.8 | 150.8 | 150.85 | 156.35 | 150.9 | 145.9 | 176.9 | 162.4 | 174.9 | 162.8 | 165.7 | 165.6 | 172.2 | 168.4 | 176.3 | 173 | 146.5 | 190.2 | 191 | 194.3 | 188.6 | 186.7 | 188 | 186.8 | 194.6 | 184.9 | 174.4
2007 | 146.9 | 143.3 | 140.3 | 134.8 | 135.4 | 206.8 | 147.7 | 143.1 | 134.8 | 141.7 | 175.1 | 173.7 | 176.7 | 177.5 | 176.2 | 174.7 | 179.1 | 173.6 | 201.1 | 175.2 | 178.2 | 185.9 | 152.6 | 155.9 | 152.3 | 179.6 | 178.3 | 179.6 | 178 | 179.5 | 178.6 | 183.3 | 179.1 | 173.4 | 163.1 | 145.6 | 139 | 148.9 | 148.1 | 131.7 | 152 | 135.8 | 148 | 140.1 | 138.1 | 136.9 | 200.4 | 148 | 148.1 | 186.5 | 160.5 | 177.7 | 166 | 175 | 159.2 | 149 | 152.6 | 147.7 | 165.4 | 154.1 | 149.7 | 149.5 | 152.7 | 152.4 | 157.6 | 148.9 | 144 | 135 | 141 | 138.7 | 147.6 | 150.9 | 139.4 | 138 | 145.2 | 132.4 | 146.4 | 148.2 | 152.5 | 191.8 | 180.4 | 179.7 | 182 | 181.7 | 179.1 | 166.8 | 169.1 | 180.4 | 166.8 | 172.5 | 172.9 | 161.7 | 137.2 | 152.6 | 158.7 | 156.1 | 174.2 | 184.5 | 171.4 | 137.7 | 131.2 | 169 | 157.8 | 170.6 | 145.3 | 147.7 | 147.8 | 147.7 | 150.3 | 166.7 | 161.4 | 159.3 | 158.7 | 179.3 | 183.3 | 185.2 | 184.6 | 181.7 | 146.7 | 159.4 | 155.7 | 168.6 | 215.2 | 163.5 | 159.8 | 159.8 | 155 | 196.5 | 132.8 | 133.7 | 131.7 | 132.1 | 131 | 139.8 | 159 | 153.2 | 152.4 | 164.9 | 155.1 | 149.4 | 158.1 | 150.3 | 161.6 | 156.7 | 136.2 | 135.6 | 132.5 | 168.5 | 169.5 | 169.4 | 156 | 159.4 | 188.4 | 163.2 | 164.9 | 163.1 | 174.4 | 139.3 | 131.7 | 129.5 | 133 | 133.7 | 130.6 | 143.1 | 144.4 | 128.5 | 132.2 | 131.6 | 137.1 | 128.8 | 138.6 | 126.2 | 134.8 | 146 | 130.2 | 125 | 136.4 | 132.1 | 132.1 | 140 | 144.6 | 144.4 | 143.2 | 155 | 146.2 | 146.1 | 146.75 | 151.15 | 147.3 | 142.9 | 171.4 | 156.7 | 168.7 | 158.7 | 160.1 | 159.4 | 164.8 | 160.7 | 168.9 | 164.7 | 141.3 | 183.1 | 184.4 | 186.8 | 182.4 | 181.7 | 182.4 | 182 | 187.7 | 180.6 | 170.1
2006 | 135.7 | 133.6 | 126.7 | 124 | 122.2 | 196.4 | 137.9 | 134.8 | 123.2 | 127.2 | 166.8 | 164.9 | 169.8 | 167.3 | 167.4 | 166 | 172.2 | 164 | 191.2 | 166.4 | 171 | 177.9 | 146.1 | 149.2 | 145 | 169.5 | 168 | 169.5 | 167.7 | 169.8 | 169.7 | 173.7 | 169.1 | 158.3 | 153 | 136 | 126.5 | 136.7 | 134.3 | 118.4 | 136.6 | 123.6 | 139.9 | 126.3 | 124.3 | 124 | 191.9 | 141.6 | 141.2 | 177.8 | 153.8 | 168.7 | 155.2 | 163.3 | 152.8 | 139.8 | 144.4 | 139.1 | 154.5 | 144.6 | 141.2 | 141.3 | 144 | 145.8 | 151.1 | 142.9 | 137.3 | 128.4 | 134.7 | 132.9 | 129 | 143 | 129.4 | 129.8 | 135.8 | 125.2 | 140.2 | 139.8 | 144.9 | 180.4 | 171.6 | 170.4 | 172.3 | 173.5 | 170.4 | 157.3 | 159.7 | 171.6 | 161.1 | 165.5 | 165.8 | 153.8 | 131.1 | 146 | 152.5 | 150.6 | 166.2 | 173.9 | 161.9 | 123.3 | 117.1 | 162 | 152.4 | 159.3 | 139.4 | 140.5 | 140.8 | 132.4 | 140.7 | 160 | 154.5 | 146.7 | 146.4 | 167.7 | 171 | 173.6 | 172.2 | 169.9 | 140.1 | 151.6 | 147.5 | 159.2 | 204.5 | 155.2 | 151.1 | 150.9 | 146.4 | 186 | 125.1 | 124.6 | 123.8 | 124.2 | 123 | 133.2 | 152.8 | 147 | 144.9 | 156.9 | 146.9 | 142.9 | 151.8 | 143.4 | 154.5 | 150.3 | 129.5 | 129.5 | 125.7 | 160.5 | 161.7 | 160.1 | 148.7 | 150.7 | 177.8 | 155.5 | 155 | 153.9 | 163.6 | 122.4 | 118.7 | 122.8 | 126.6 | 127 | 123.9 | 136.5 | 135.5 | 121.6 | 125.7 | 125.5 | 130.1 | 122 | 131.1 | 120.3 | 127.6 | 138.2 | 123.2 | 118.3 | 129.8 | 125.2 | 125.3 | 133.4 | 137.7 | 131.7 | 130.7 | 146.2 | 133.7 | 134.6 | 134.25 | 140.5 | 134.8 | 129.7 | 162.9 | 150.1 | 160.7 | 149.4 | 151.4 | 152.7 | 157.1 | 152.8 | 158.8 | 157.2 | 128 | 163.6 | 164.8 | 169 | 164.9 | 158.6 | 163.7 | 159 | 170.6 | 169.3 | 155.9
2005 | 127.9 | 125.4 | 119.3 | 116.6 | 114.6 | 185.6 | 128.5 | 124.1 | 115.4 | 119.4 | 156.5 | 153 | 157.9 | 157.1 | 156.4 | 155.4 | 161.1 | 153.8 | 179.7 | 155.7 | 160 | 167.2 | 138.3 | 141.1 | 136.4 | 160.8 | 159.4 | 159.6 | 159.1 | 160.8 | 160.9 | 164.1 | 160.5 | 149.6 | 142.7 | 126 | 119.2 | 127.1 | 126 | 110.7 | 127.7 | 115.7 | 131.7 | 118.9 | 116.1 | 116.9 | 181.2 | 133.8 | 132.5 | 164.4 | 145 | 158.3 | 146.5 | 151.2 | 145.4 | 131.4 | 136.2 | 131 | 146.4 | 137.4 | 131 | 133.8 | 135.2 | 135.7 | 142.1 | 133.5 | 129.4 | 120 | 125.9 | 125.6 | 121.5 | 135.1 | 120.8 | 117.7 | 126.2 | 117.4 | 131.7 | 131.4 | 135.8 | 169.6 | 161.3 | 159.6 | 162.2 | 162.3 | 159.6 | 147.6 | 150.7 | 158.8 | 147.5 | 155.8 | 156.2 | 145.1 | 123.1 | 134.9 | 142 | 140.6 | 157.3 | 164.6 | 152.8 | 116 | 109.9 | 151.3 | 143.1 | 149.4 | 131.7 | 131.9 | 132.4 | 124.1 | 132.8 | 149.5 | 145.4 | 136.8 | 136.5 | 159 | 162.4 | 163.9 | 163 | 161.5 | 130.4 | 142.2 | 137.5 | 149.4 | 194 | 147.3 | 142.2 | 141.9 | 136.9 | 176.1 | 110.5 | 112.1 | 112.1 | 112.1 | 111.1 | 125.3 | 144.4 | 137.7 | 136.8 | 147.9 | 138 | 134.5 | 143.3 | 134.8 | 145.5 | 141.1 | 121.6 | 121.6 | 117.8 | 150.9 | 152.2 | 150.2 | 140.6 | 141.5 | 166.4 | 146.6 | 145.5 | 142.9 | 155.6 | 110.2 | 109.6 | 115.2 | 118.5 | 116 | 115.1 | 128.6 | 127.9 | 113.8 | 117.3 | 117.9 | 121.3 | 114.4 | 123.7 | 112.5 | 119.4 | 129 | 115.5 | 110.5 | 121.3 | 116.1 | 117.3 | 126 | 129.4 | 124.6 | 123.8 | 136.5 | 123.5 | 124.4 | 124.45 | 130.95 | 125.4 | 112.2 | 153.9 | 141.9 | 151.5 | 140.8 | 141 | 144.4 | 148.3 | 145.2 | 148.4 | 147.9 | 118.9 | 154.4 | 155.7 | 160 | 156.2 | 149.2 | 155.1 | 150.1 | 162.6 | 159.4 | 146.9
2004 | 115.9 | 112.9 | 107 | 104.9 | 102.9 | 167 | 116.5 | 113.6 | 103.8 | 108.6 | 142.1 | 139.5 | 143.8 | 142 | 140.9 | 141 | 147.2 | 139 | 163.6 | 141.4 | 144.2 | 148.6 | 125.6 | 127.2 | 123.5 | 143.6 | 142.9 | 142.4 | 142.7 | 144.3 | 143.6 | 146.5 | 143.2 | 136.1 | 126.8 | 114.8 | 107.8 | 115.6 | 113.2 | 100.6 | 116.6 | 102.8 | 119.6 | 102 | 105 | 105.6 | 161.2 | 122 | 120.5 | 149.3 | 129.3 | 145.1 | 133.9 | 138.1 | 130.3 | 120.9 | 123.5 | 120.1 | 132.2 | 125 | 120 | 120.6 | 123 | 122.7 | 128.6 | 121.6 | 116.2 | 108.3 | 112.6 | 113.4 | 110.1 | 120.3 | 105.6 | 109 | 115.3 | 105.7 | 119.8 | 119.4 | 121.4 | 154.1 | 144.4 | 143.6 | 146.4 | 146.7 | 143.6 | 131.9 | 136.5 | 143.2 | 135.9 | 142.1 | 141.9 | 129.6 | 112.8 | 122.5 | 129.7 | 127.6 | 139.1 | 150.1 | 137 | 105.3 | 99.3 | 135.1 | 126.9 | 135.5 | 116.3 | 118.2 | 117.9 | 112.1 | 119.4 | 137.1 | 130.5 | 124.2 | 123.9 | 143.4 | 145.4 | 147.2 | 146.6 | 146 | 118.3 | 128.6 | 123.5 | 136.1 | 177.7 | 132 | 128.4 | 127.3 | 124.4 | 161.8 | 98.9 | 100 | 100.1 | 100.3 | 99.4 | 113 | 131.9 | 125.6 | 124.3 | 135.6 | 126.2 | 121.1 | 131.5 | 122 | 132.8 | 129.3 | 109.3 | 109.4 | 107.3 | 136.8 | 137.8 | 133.9 | 127 | 126.2 | 148.4 | 133.1 | 128.7 | 129 | 138.8 | 98.9 | 98.4 | 103.9 | 107.3 | 105 | 104.5 | 115.6 | 115.8 | 102.9 | 106.3 | 105.7 | 108.5 | 102.9 | 112 | 101.5 | 108.4 | 115.9 | 104.7 | 99.9 | 108.4 | 104.8 | 105.1 | 115.2 | 117.8 | 113 | 112.3 | 121.5 | 108.9 | 110.2 | 109.9 | 116.2 | 110.9 | 99.7 | 138 | 127.6 | 134.5 | 124.8 | 125.6 | 128.9 | 132.4 | 129.7 | 134.2 | 132.7 | 104.7 | 138.8 | 139.4 | 142.6 | 140.4 | 134.5 | 141 | 135.7 | 146 | 141.7 | 129.7
2003 | 113.1 | 110.7 | 104.8 | 102.6 | 100.8 | 163.5 | 113.9 | 110.6 | 101.8 | 105.8 | 139.4 | 137.2 | 142.1 | 139.6 | 138.7 | 138.7 | 144.9 | 136.6 | 162.1 | 139.2 | 141.8 | 146.4 | 123.1 | 123.7 | 120.7 | 141.3 | 140.2 | 140.3 | 140 | 141.6 | 140.6 | 145.1 | 140.8 | 133 | 124.6 | 109 | 105.6 | 110.5 | 107.8 | 98 | 103.5 | 100.5 | 115.8 | 99.1 | 102.7 | 103 | 159.4 | 120.2 | 118.7 | 146.2 | 127.4 | 143.5 | 132.4 | 137.3 | 128.4 | 119.7 | 121.4 | 118.2 | 131.4 | 122.5 | 118.7 | 119.2 | 121.7 | 120.9 | 126.4 | 120.2 | 114.6 | 105.9 | 109.4 | 111.3 | 107.8 | 118.7 | 103.3 | 106.1 | 112.4 | 103.9 | 117.7 | 117.3 | 118.1 | 150.2 | 139.6 | 140.6 | 143.3 | 143.6 | 140.5 | 128.9 | 133.8 | 139 | 134.1 | 139 | 138.7 | 127.9 | 110.9 | 120.8 | 127.7 | 126 | 136.7 | 146.5 | 134.5 | 101.4 | 96.7 | 131.9 | 124.8 | 133.3 | 113.9 | 115.8 | 115.8 | 110.2 | 117.3 | 133.8 | 128.3 | 122.4 | 122.2 | 142 | 144.3 | 145.7 | 145 | 143 | 116.4 | 126.8 | 121.8 | 132.8 | 173.4 | 130.3 | 126.7 | 124.7 | 121.7 | 160 | 96.2 | 97.5 | 97.5 | 97.8 | 96.8 | 110.6 | 129.6 | 123.7 | 121.3 | 132.7 | 123.7 | 119.4 | 126.1 | 120 | 130.4 | 126.2 | 107.5 | 107.8 | 105 | 134.2 | 135.9 | 130.3 | 124.5 | 123.8 | 145.5 | 130.5 | 126.3 | 126 | 135.9 | 96.1 | 95.7 | 101.3 | 104 | 102.8 | 102.3 | 111.1 | 110.9 | 100.5 | 104.4 | 103.9 | 106.1 | 100.4 | 109.3 | 99.5 | 105.5 | 113.4 | 102.3 | 97.6 | 104.8 | 102.7 | 103 | 112.7 | 116 | 110.7 | 110.1 | 119.5 | 104.8 | 106.2 | 106.7 | 114.05 | 108.6 | 97 | 134.9 | 125.9 | 133 | 123.3 | 123.6 | 127.4 | 130.9 | 128.4 | 131.1 | 131.5 | 102.6 | 133.6 | 134.2 | 139.1 | 137 | 130.2 | 137.4 | 131.4 | 142.3 | 137 | 124.4
2002 | 110 | 103.4 | 103.6 | 101.7 | 99.7 | 159.5 | 113.3 | 110.2 | 100.4 | 102.1 | 136.5 | 133.4 | 136 | 136.4 | 136.3 | 135.3 | 138.4 | 134.2 | 157.9 | 135.9 | 136.9 | 143.8 | 118.7 | 121.3 | 116.7 | 133.8 | 133.6 | 133.1 | 133.3 | 134.8 | 133.5 | 136.2 | 133.9 | 129.4 | 120.3 | 107.1 | 104.6 | 107.4 | 106.7 | 97.3 | 102.8 | 99.7 | 113 | 98.3 | 101.9 | 102 | 157.2 | 118.3 | 117.1 | 141.2 | 123.8 | 138.5 | 129.6 | 132.9 | 125.3 | 117.5 | 119 | 116.4 | 129.1 | 120.5 | 116.7 | 117.1 | 119.9 | 116 | 122.1 | 116.7 | 111.4 | 103.7 | 107.8 | 109.6 | 106.2 | 116.4 | 102.5 | 105 | 110.6 | 102.1 | 117.5 | 117.1 | 115.6 | 145.6 | 136 | 135 | 136.9 | 137.3 | 134.9 | 124.7 | 128.3 | 134.9 | 131.4 | 134.3 | 134.2 | 126.9 | 107.4 | 119.9 | 125.3 | 124.4 | 131.9 | 139.5 | 130 | 101 | 96.3 | 128.4 | 122.7 | 129.6 | 112.5 | 114.6 | 114.5 | 108.2 | 115 | 131.9 | 126.4 | 119.9 | 119.6 | 135.9 | 138.5 | 140.2 | 140.1 | 137.6 | 114.6 | 122.6 | 119 | 128.5 | 170.1 | 127.1 | 123 | 121.8 | 118.4 | 154.8 | 94.8 | 96.1 | 96.1 | 96.3 | 95.5 | 106.3 | 127.2 | 120.9 | 119.2 | 130 | 120.9 | 117.5 | 124.3 | 118 | 128.4 | 123.6 | 106.3 | 106 | 104.1 | 132.2 | 133.9 | 128.1 | 122.1 | 121.1 | 142 | 127.8 | 123.4 | 124.2 | 131.1 | 94.8 | 93.9 | 100.2 | 103.2 | 102.2 | 101.2 | 107.6 | 109.2 | 99.9 | 101.9 | 102.4 | 104.5 | 98.9 | 107.9 | 98.7 | 104.6 | 111.5 | 100.5 | 95.9 | 103.7 | 100.5 | 101.4 | 110.8 | 113.7 | 109 | 108.4 | 115.1 | 102.9 | 104.1 | 104.75 | 110.85 | 106.6 | 95.2 | 132.7 | 123.9 | 131.4 | 121.2 | 120.9 | 123 | 127.3 | 124.5 | 128.2 | 126.5 | 101.7 | 122.5 | 122.2 | 136.3 | 134.1 | 127.2 | 134.9 | 128.4 | 139.8 | 134.6 | 121.4
2001 | 106 | 100.5 | 100.6 | 98.3 | 95.9 | 152.6 | 109 | 106.4 | 97.3 | 98.7 | 132.5 | 129.3 | 132.8 | 132.4 | 132.4 | 131.4 | 135.5 | 129.7 | 151.8 | 131.5 | 134.1 | 140.2 | 113.3 | 117.2 | 113.1 | 128.6 | 128.5 | 128.5 | 128.3 | 128.6 | 128.2 | 131.5 | 128.8 | 124.8 | 115.9 | 104.3 | 100.8 | 104.6 | 103.8 | 94.8 | 100.3 | 96.4 | 109.1 | 95.5 | 99 | 99 | 150 | 114.3 | 113.4 | 135.8 | 120.1 | 133.7 | 124.3 | 127.8 | 119.8 | 113.4 | 115.6 | 112.1 | 123.4 | 116.4 | 112.8 | 111.6 | 115.5 | 112.5 | 117.5 | 113.2 | 107.7 | 100.6 | 104.3 | 105.2 | 103.3 | 112.7 | 99.4 | 101.3 | 104.6 | 98.3 | 114.6 | 114.3 | 111.7 | 140.9 | 132.1 | 131.4 | 133.1 | 132.9 | 131.3 | 120.3 | 124.5 | 130.1 | 126.8 | 129.8 | 129.4 | 122.4 | 104.3 | 115.2 | 120.1 | 119.7 | 131.4 | 136.1 | 124.9 | 98.7 | 93.9 | 121.8 | 114.7 | 125.5 | 106.7 | 117.5 | 117.7 | 101.3 | 111.6 | 127.8 | 122.5 | 116.2 | 116.2 | 133.4 | 136.7 | 136.9 | 136.8 | 136 | 111.4 | 119.2 | 116 | 125.2 | 164.4 | 123.1 | 120.1 | 118.6 | 115.3 | 151.4 | 91.5 | 92.9 | 92.9 | 93.3 | 92.3 | 103.1 | 123.5 | 117.7 | 115.9 | 125.9 | 117.1 | 114 | 120.4 | 114.7 | 123.8 | 119.9 | 102 | 102.1 | 99.7 | 129.8 | 131.2 | 123.5 | 118.9 | 118.4 | 136.9 | 124.1 | 120.4 | 121.1 | 127.8 | 92.1 | 91.3 | 96.8 | 99.7 | 98.2 | 96.5 | 102.6 | 104.3 | 93.4 | 98.4 | 99.8 | 102.3 | 96.6 | 103.8 | 95.5 | 100.9 | 107.8 | 97.6 | 93.4 | 100.5 | 97.8 | 97.3 | 107.7 | 109.1 | 105.7 | 105.2 | 110.8 | 99.8 | 100.3 | 101.35 | 106.85 | 102.9 | 92.1 | 127.9 | 120.3 | 125.7 | 114.6 | 117.5 | 119.1 | 123.6 | 120.6 | 123.9 | 123.3 | 99 | 117.5 | 117.4 | 131.5 | 129.1 | 124.4 | 130.2 | 125.5 | 134.7 | 130.2 | 117.2
2000 | 104.1 | 98.9 | 99.1 | 94.2 | 94.6 | 148.3 | 106.9 | 104.9 | 94.4 | 95.7 | 129.4 | 125.2 | 129.4 | 129.9 | 129.7 | 128 | 131.5 | 127.1 | 146.9 | 128.7 | 130.7 | 137.1 | 109.8 | 111.8 | 108.8 | 122.7 | 122.6 | 122.9 | 122.4 | 122.7 | 121.5 | 126.4 | 123.2 | 117.4 | 113.8 | 102.4 | 99 | 101.8 | 101.2 | 93.6 | 98.9 | 94.9 | 106.1 | 94.1 | 97 | 97.5 | 144.8 | 112.9 | 112.1 | 131.2 | 115.1 | 124.6 | 119 | 122.2 | 116.2 | 109.8 | 111.5 | 108.4 | 117.8 | 113.2 | 109.1 | 106.9 | 110.8 | 108.8 | 112.6 | 108.9 | 99 | 98.1 | 101 | 101.1 | 101.4 | 109.3 | 97.8 | 99.7 | 102.1 | 96.2 | 105.7 | 105.4 | 107.7 | 138.9 | 129.4 | 128.4 | 129.7 | 130.3 | 128.3 | 116.7 | 121 | 127.3 | 124.3 | 125.8 | 125.3 | 119.8 | 102.7 | 111.6 | 117.6 | 115.9 | 124.1 | 131.1 | 120.1 | 97.2 | 92.9 | 118.2 | 111.9 | 122.4 | 104.3 | 113.7 | 113.9 | 98.8 | 107 | 125.8 | 118.2 | 111.9 | 111.9 | 128.4 | 130.5 | 132.6 | 132.4 | 130.6 | 109 | 116.5 | 112.4 | 122.3 | 159.2 | 120 | 117.5 | 115.1 | 112.4 | 144.8 | 90.3 | 91.6 | 91.6 | 91.9 | 91 | 97.9 | 117.8 | 112.7 | 110.1 | 121.3 | 112.5 | 109 | 115 | 109.2 | 115.7 | 114.1 | 98.7 | 98.9 | 97.5 | 126.3 | 127.4 | 119.9 | 114.6 | 114 | 132.1 | 120.9 | 115.9 | 117.7 | 122.8 | 89.9 | 89.1 | 94.2 | 98 | 96.9 | 95 | 100.8 | 100.8 | 93.4 | 98.1 | 99.1 | 101.6 | 96.9 | 102.7 | 92.4 | 99.9 | 106 | 97.6 | 93.4 | 99.4 | 97.3 | 96.9 | 104.6 | 106.5 | 98.9 | 98.3 | 108.1 | 96.5 | 97.6 | 98.35 | 104.15 | 100.2 | 90.7 | 124.6 | 118.3 | 122.9 | 111.5 | 114.4 | 114.6 | 119.1 | 116.6 | 120.5 | 118.7 | 98.1 | 115.9 | 115.8 | 130 | 127.5 | 122.8 | 128.8 | 124.1 | 133.1 | 128.4 | 115.6
1999 | 101.2 | 97.4 | 97.7 | 92.5 | 92.8 | 145.9 | 105.5 | 103.3 | 93.1 | 94.4 | 127.9 | 123.6 | 126.9 | 128.7 | 128.2 | 126.5 | 129.4 | 124.9 | 145.1 | 127.2 | 127.9 | 135.3 | 107 | 109.1 | 107.1 | 121.1 | 121.3 | 121.2 | 121.1 | 121.3 | 120 | 122 | 121.2 | 116.6 | 111.5 | 101.4 | 98 | 100.8 | 100.1 | 92.5 | 97.9 | 93.5 | 102.9 | 92.8 | 95.8 | 96 | 143 | 110.2 | 109.6 | 129.6 | 113 | 122.6 | 116.4 | 120.7 | 113.8 | 107.1 | 109.3 | 106.8 | 112.8 | 110.6 | 105.7 | 103.7 | 107.9 | 104.1 | 109.2 | 107.6 | 96.7 | 96.4 | 98.7 | 99.3 | 99.7 | 106.6 | 96.1 | 97.6 | 99.5 | 94.8 | 105 | 104.7 | 106.4 | 136.2 | 126.7 | 126.3 | 127.3 | 127.4 | 126.2 | 115 | 118.8 | 123.8 | 117.5 | 122.7 | 122.6 | 113.7 | 100.9 | 106.1 | 111.5 | 110.1 | 120.3 | 126.5 | 117.1 | 95.7 | 91.8 | 114.9 | 106.1 | 119.8 | 101.1 | 112.1 | 112.7 | 96.6 | 104.8 | 121.9 | 114.4 | 109.6 | 109.6 | 125.3 | 128.8 | 131.6 | 129.5 | 129.6 | 106.7 | 114.6 | 108.6 | 120.2 | 155.9 | 116.8 | 114.7 | 113.7 | 108.5 | 140.6 | 89.3 | 90.2 | 90.3 | 90.5 | 90.1 | 96.8 | 116 | 110.6 | 107.9 | 118.7 | 109.5 | 107.1 | 112 | 106.4 | 113.6 | 111.9 | 97.5 | 97.4 | 96.2 | 120.9 | 124.3 | 117.8 | 113.8 | 112.8 | 129.8 | 119.6 | 114.8 | 116.3 | 121.6 | 89 | 88.1 | 92.4 | 95.8 | 95.9 | 93.4 | 99.7 | 98.6 | 91.8 | 94.5 | 96 | 99.7 | 94 | 101 | 90.7 | 97.6 | 104.6 | 96 | 92.1 | 98 | 94.8 | 95.5 | 103.3 | 104.5 | 98.2 | 97.7 | 106.1 | 95.6 | 96.5 | 97.2 | 102.45 | 98.8 | 89.8 | 123.3 | 116.7 | 121.6 | 110.6 | 113.4 | 112.1 | 115.8 | 115.9 | 117.4 | 115.5 | 96.9 | 115.3 | 115.2 | 128.1 | 125.6 | 120.8 | 126.8 | 121.9 | 131.2 | 127.1 | 115.2
1998 | 96.2 | 94 | 94.8 | 90.3 | 89.8 | 143.8 | 102.1 | 101 | 90.6 | 91.4 | 125.2 | 120.3 | 123.9 | 125.8 | 124.7 | 123.7 | 125.9 | 121.3 | 141.9 | 123.7 | 124.7 | 132.5 | 103.3 | 106.5 | 103.7 | 119.1 | 119.4 | 120 | 119.7 | 120 | 118.8 | 120.8 | 120.1 | 112.3 | 109.6 | 99.4 | 96.2 | 99 | 98.4 | 90.9 | 96.3 | 91.4 | 100.8 | 90.4 | 93.3 | 93.7 | 140.4 | 107.4 | 107 | 125.2 | 110.1 | 119.8 | 113.8 | 115.5 | 111.1 | 105 | 107.2 | 104.5 | 111.1 | 108 | 103.6 | 102.3 | 106 | 102.5 | 106.8 | 103.8 | 95.1 | 94.8 | 97.4 | 97.4 | 97.4 | 101.5 | 94.7 | 96.1 | 97.7 | 92 | 102.8 | 102.5 | 104.1 | 132.8 | 125 | 124.7 | 125 | 125.3 | 124.6 | 114.2 | 117.1 | 122.6 | 116 | 119.7 | 119.5 | 112.3 | 99.7 | 104.9 | 110.1 | 108.7 | 117.7 | 124.6 | 115.5 | 92.1 | 89.5 | 108.2 | 104.2 | 115.9 | 98.9 | 109.7 | 109.1 | 94.9 | 101.2 | 118.1 | 111.4 | 110.1 | 110 | 124.3 | 127.7 | 128.9 | 128.5 | 127.9 | 103.8 | 113 | 109 | 119.1 | 154.4 | 117.2 | 114.2 | 113.6 | 108.6 | 141.4 | 88.2 | 89.1 | 89.2 | 89.4 | 89 | 95.2 | 113.1 | 108.5 | 105 | 114.8 | 106.8 | 104.5 | 109.4 | 104.1 | 111.2 | 109 | 94.3 | 94.5 | 94.5 | 120 | 122.2 | 115.7 | 109.8 | 110.5 | 126.6 | 117.1 | 112.5 | 113.7 | 120.3 | 88 | 87.2 | 90.7 | 93.6 | 94.9 | 92.4 | 97.2 | 96.8 | 89.8 | 92.7 | 94.2 | 97.9 | 91.8 | 97.9 | 88.4 | 94.5 | 101.3 | 93.3 | 90.1 | 94.8 | 92.7 | 92.9 | 98.5 | 99.5 | 97.8 | 97.3 | 104.1 | 93.7 | 93.9 | 95.35 | 100.55 | 97 | 88.3 | 119.4 | 114.3 | 118.3 | 106.7 | 109 | 109.5 | 112.9 | 110.8 | 113.4 | 112.7 | 95.4 | 112.5 | 112.4 | 126.3 | 123.9 | 119 | 124.7 | 119.6 | 128.5 | 123.8 | 113.7
From RSMeans, Historical Cost Index Data 2024
Copyright Gordian.
30 Patewood Dr. Suite 350, Greenville, SC, 29615; All rights reserved

## DP Estimate
DGS-30-199
Detailed Planning Cost Estimate
| Description |  | Amount Required For Complete Project | Percent Required For Detailed Planning | Amount Required For Detailed Planning | Percent Required For Bid Documents | Amount Required For Bid Documents
Design & Related Services
| A/E Basic Services |  | 4284558.7647 | 40% | 1713823.5059 | 80% | 3427647.0118
| A/E Additional Services |  | 85691.1753 | 40% | 34276.4701 | 80% | 68552.9402
| A/E Reimbursables |  | 42845.5876 | 40% | 17138.2351 | 80% | 34276.4701
| Specialty Consultants (Food Services, Acoustics, etc.) |  | 0 | 100% | 0 | 100% | 0
| CM Design Phase Services |  | 345528.9326 | 40% | 138211.5731 | 100% | 345528.9326
| Subsurface Investigation (Geotech, Soil Borings) |  | 40000 | 100% | 40000 | 100% | 40000
| Land Survey |  | 12000 | 100% | 12000 | 100% | 12000
| Archeological Survey |  | 40000 | 100% | 40000 | 100% | 40000
| Hazmat Survey & Design |  | 0 | 100% | 0 | 100% | 0
| Value Engineering Services |  | 0 | 100% | 0 | 100% | 0
| Cost Estimating Services |  | 0 | 100% | 0 | 100% | 0
| Other Design & Related Services (list): |  |  |  | 0 |  | 0
|  | Environmental Impact Report (EIR) | 0 | 100% | 0 | 100% | 0
|  |  | 0 | 40% | 0 | 80% | 0
| Design & Related Services Total |  |  |  | 1995449.7841 |  | 3968005.3547
Project Management & Other Costs
| Agency Project Management |  | 1632894.7368 | 40% | 653157.8947 | 55% | 898092.1053
| Work By Owner (List): |  | 0 | 0% | 0 | 0% | 0
|  | DGS Division of Real Estate services | 25000 | 0% | 0 | 0% | 0
|  |  | 0 | 0% | 0 | 0% | 0
| BCOM Services |  | 1382115.7305 | 40% | 552846.2922 | 80% | 1105692.5844
| Advertisements |  | 6000 | 40% | 2400 | 100% | 6000
| Printing & Reproduction | Abatement Design | 20000 | 40% | 8000 | 80% | 16000
| Moving & Relocation Expenses | Abatement • | 99606.0606 | 0% | 0 | 0% | 0
| Data & Voice Communications |  | 327745.15 | 0% | 0 | 0% | 0
| Signage |  | 130318.1818 | 0% | 0 | 0% | 0
| Demolition | Soil Borings | 200000 | 0% | 0 | 0% | 0
| Hazardous Material Abatement | Geotechnical Report | 0 | 0% | 0 | 0% | 0
| Utility Connection Fees |  | 100000 | 0% | 0 | 0% | 0
| Utility Relocations |  | 50000 | 0% | 0 | 0% | 0
| Commissioning |  | 260636.3636 | 40% | 104254.5455 | 50% | 130318.1818
| Miscellaneous Other Costs (List): |  | 0 |  | 0 |  | 0
|  | Miscellaneous site acquisition soft costs | 0 | 0% | 0 | 0% | 0
|  |  | 0 | 0% | 0 | 0% | 0
| Project Management & Other Costs Total |  |  |  | 1320658.7324 |  | 2156102.8715
Totals
| Total Costs |  |  |  | 3316108.5165 |  | 6124108.2263

## Escalation (hidden)
| Category | Note | Description of Duration | Starting Amount | Starting Date | End Date | Duration | Rate | End Amount
Escalation Tool For Agency Use
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
No Data Entry Beyond This Point | [10 empty] | Multiplier
| Construction | 2 | The amount requried for construction, shown in the blue highlighted cell on the Overview tab, includes escalation and supply chain premium to the mid-point of construction. | 69105786.5273 | 2024-01-01 | 2024-12-31 | 1 | 4% | 71870017.9883 | 01/01/2024 to minimum of YearEnd or Constuction Mid.
|  |  |  | 71870017.9883 | 2025-01-01 | 2025-12-31 | 0.99726 | 4% | 74736787.509 | 01/01/2025 to minimum of YearEnd or Constuction Mid. | 1.2046
|  |  |  | 74736787.509 | 2026-01-01 | 2028-09-30 | 2.7479 | 4% | 83241732.247 | 01/01/2026 to minimum of YearEnd or Constuction Mid.
| Design & Related Services | 3 | The amount required for soft costs, shown in the blue highlighted cell on the Overview tab, includes escalation to the start of construction. | 4850624.4603 | 2024-01-01 | 2027-10-01 | 3.7507 | 4% | 5619327.4683 | 01/01/2024 to Constuction Start. | 1.1585
| Inspection & Testing Services | 3 | The amount required for soft costs, shown in the blue highlighted cell on the Overview tab, includes escalation to the start of construction. | 548907.8947 | 2024-01-01 | 2027-10-01 | 3.7507 | 4% | 635896.1069 | 01/01/2024 to Constuction Start. | 1.1585
| Project Management & Other Costs | 3 | The amount required for soft costs, shown in the blue highlighted cell on the Overview tab, includes escalation to the start of construction. | 4234316.2235 | 2024-01-01 | 2027-10-01 | 3.7507 | 4% | 4905349.746 | 01/01/2024 to Constuction Start. | 1.1585
| Furnishings & Movable Equipment | 4 | The amount required for FF&E, shown in the blue highlighted cell on the Overview tab, includes escalation and supply chain premium to the end of construction. | 1954772.7273 | 2024-01-01 | 2024-12-31 | 1 | 4% | 2032963.6364 | 01/01/2024 to minimum of YearEnd or Constuction Mid.
|  |  |  | 2032963.6364 | 2025-01-01 | 2025-12-31 | 0.99726 | 4% | 2114055.0059 | 01/01/2025 to minimum of YearEnd or Constuction Mid. | 1.2527
|  |  |  | 2114055.0059 | 2026-01-01 | 2029-09-30 | 3.7479 | 4% | 2448816.853 | 01/01/2026 to minimum of YearEnd or Constuction Mid.
| Construction Contingency | 2 | The amount requried for construction, shown in the blue highlighted cell on the Overview tab, includes escalation and supply chain premium to the mid-point of construction. | 1382115.7305 | 2024-01-01 | 2024-12-31 | 1 | 4% | 1437400.3598 | 01/01/2024 to minimum of YearEnd or Constuction Mid.
|  |  |  | 1437400.3598 | 2025-01-01 | 2025-12-31 | 0.99726 | 4% | 1494735.7502 | 01/01/2025 to minimum of YearEnd or Constuction Mid. | 1.2046
|  |  |  | 1494735.7502 | 2026-01-01 | 2028-09-30 | 2.7479 | 4% | 1664834.6449 | 01/01/2026 to minimum of YearEnd or Constuction Mid.
| Detailed Planning Phase | 3 | The amount required for soft costs, shown in the blue highlighted cell on the Overview tab, includes escalation to the start of construction. | 3316108.5165 | 2024-01-01 | 2026-10-01 | 2.7507 | 4% | 3693874.0543 | 01/01/2024 to half-way to start of construction. | 1.1139
| Total Planning to Bid Phase | 3 | Total Planning to Bid Phase | 6124108.2263 | 2024-01-01 | 2027-10-01 | 3.7507 | 4% | 7094626.652 | 01/01/2024 to Constuction Start. | 1.1585
Formulas:
End Date = MIN(DATE(YEAR([Starting Date]),12,31),Overview!$C47)
End Date = MIN([Starting Date]+364,Overview!$C47)

## Inst - Writ
< Return to Index
Instructions:
Data entry cells:
Pull down cells:
This Project Planner (CR-1) is designed to assist in submitting a capital budget request (CBR). All or part may be used. The Overview, Agency Narrative, and Budget tabs mirror the CBR data requested in Virginia’s Performance Budgeting System (PB). Since this is a stand-alone file, CBRs can be worked on prior to the opening of PB each spring. Additionally, this file can be easily archived and updated in future years simply by updating the current date. If the annual escalation rate, on the Overview tab, is different than the current CR-1, the project information will need to be transferred over to a new CR-1. A completed example is also available on the DEB Forms site.
General information: - Open field data entry cells are light yellow. - Pull-downs are gray. - Links are 3-D
Additional information per tab (not in order as viewed in the CR-1):
Overview tab:
This tab is a summary of the project. General information such as project name, sf, and schedule is noted here. Other information is populated from other tabs. The aspects of this tab that differ from PB are as follows: - Amount (mid-construction) are the Amounts (current date) escalated based on schedule information entered on this tab. - Parking is broken down to differentiate the net # of new parking spaces for surface lots or parking decks. If a new building is built in an existing parking lot and displaces 200 parking spaces but the project builds a new 300 space parking lot, then the net number of parking spaces is 100.
Agency Narrative tab:
This tab contains the same information requested in PB.
Budget tab:
This tab contains the same information requested in PB except that it also includes an additional column where the individual costs are escalated to mid-construction based upon hard-coded escalation rate and schedule information entered on the Overview tab.
Drawing tab:
This is a blank tab provided as a place to insert an image that represents the aesthetic intent. The image could be a photo of one of the comparable projects (comps) or it could simply be an image of a generic building found on the internet that represents the desired aesthetic for the project.
Blender tab:
- This tab was designed to simplify calculating the construction costs. It accomplishes this by “blending” various inputs from the comps tabs and estimate tab. - Enter "Quantity” in light yellow cells to identify the quantity of each part to produce a blended estimate. - The unit prices come from the Comps tabs and the Estimate tab. - The Blender can blend three different building types as well as incorporate the estimate sum. It produces an overall cost per sf, as identified on the Overview tab, by blending all this information proportionally.
As noted above, the Blender accommodates three different building types. Each of these three building types are identified with the following tabs:
Building Type 1, 2, and 3 Program tabs:
These makeup a very simplistic architectural program in which spaces are listed as net sf. The total of these spaces is inflated by the efficiency percentage listed at the top. This percent is based on CPSM section 6.1.2.4 – Building Efficiency Ratios. This program is not intended to replace a comprehensive architectural program study performed by a professional programming consultant. Use of this program is optional, as are all parts of the CR-1.
Building Type 1, 2, and 3 Attributes tabs:
These tabs allow the project’s characteristics to be described using convenient pull-downs and open field text boxes for the various parts of the Uniformat Level 1 categories (A. Structure, B. Shell, C. Interiors, D. Services, E. Equipment & Furnishings, Soil Conditions, and Other Distinguishing Features). Other pull-downs allow project type (new/renovation) as well as building type to be entered.
Building Type 1, 2, and 3 Comps tabs:
These tabs accommodate listing comparable projects (comps). Through the use of RS Means Historical Cost Index (HCI), those comps can be escalated to the current date and city specified. The Comps tabs can accommodate up to three comps each. This tab also accommodates listing values from the Virginia Construction Cost Database (Virginia Database). Follow link to Virginia Database, find building type and associated cost per sq. ft. and enter cost per sq. ft. where indicated on the Comps tab. It should be assumed, unless specifically known otherwise, that Comps and Database values describe buildings with the following attributes: - Relatively flat site - Very good quality construction - Utilities are available within a reasonable distance - Soils are stable and special foundations will not be required Deviations from these assumptions may be accounted for in the Modifications section of the Comps tabs.
Estimate tab:
The estimate tab may be used to estimate the cost of unique site or building attributes not covered by comps to Virginia Database value. It may also be used as the sole contributor to the Blender tab (i.e. the entire construction value based on the information on the Estimate tab). This may be useful for utility type projects.
Cost guidance - See DEB Newsletter #53 - May 2019 >
CR-1 Cost Calculation Guidance >

## Inst - Flo-Ch
< Return to Index
PROJECT PLANNER FLOW CHART
Overview:
General agency and project info
Agency Narrative
(description and justification)
Program For Up To 3 Building Types
(list of required spaces)
Build Project
With Comps and/or Database Values
To Feed
Blender
Project Characteristics For Up To 3 Building Types
(site and building attributes)
Building Type 1 Comps and/or
Database Value
for All or
Part of Project
Building Type 2 Comps
and/or
Database Value
for All or
Part of Project
Building Type 3 Comps
and/or
Database Value
for All or
Part of Project
Blender Combines All Of These Parts To Produce a "Blended" Estiimate of Construction Costs
Construction Cost From Blender, Combined With Soft Costs Produce a Complete Capital Budget Request
Estimate
For Other Modifications

## VLOOKUPS (hidden)
FF&E Included or Excluded
2008 Chapter 1 | Excluded
2011 Chapter 890 | Included
2012 Chapter 3 | Included
2013 Chapter 806 | Excluded
2014 Chapter 1 Caboose | Excluded
2014 Chapter 2 | Included
2015 Chapter 665 | Excluded
2016 Chapter 759/769 | Excluded
2017 Chapter 836 | Excluded | DPB actually put the funds in the Chapter 3 Pool.
Future Pool | TBD

## Codes (hidden)
FIPS | PROJECT_TYPE
001 - Accomack Co. | ACCESS CARD
003 - Albemarle Co. | ACCESSIBILITY IMPROVEMENT
510 - Alexandria, City Of | ACQUISITION
005 - Alleghany Co. | AGRICULTURAL
007 - Amelia Co. | AIRPORT
009 - Amherst Co. | AMPHITHEATER
011 - Appomattox Co. | AREA LIGHTING
013 - Arlington Co. | ARENA
015 - Augusta Co. | ARMORY
017 - Bath Co. | ASBESTOS & LEAD PAINT
019 - Bedford Co. | ASSEMBLY
515 - Bedford, City Of | ATHLETIC FACILITY
021 - Bland Co. | AUDITORIUM
023 - Botetourt Co. | BOAT PIER
520 - Bristol, City Of | BOATING ACCESS
025 - Brunswick Co. | BOILERS
027 - Buchanan Co. | BOOKSTORE
029 - Buckingham Co. | CABINS
530 - Buena Vista, City Of | CAMPGROUND
031 - Campbell Co. | CEMETERY
033 - Caroline Co. | CENTRAL PLANT
035 - Carroll Co. | CHILDCARE
036 - Charles City Co. | CHILLER
037 - Charlotte Co. | CLASSROOM
540 - Charlottesville, City Of | CLASSROOM/ASSEMBLY
550 - Chesapeake, City Of | CLASSROOM/K-12
041 - Chesterfield Co. | CLASSROOM/LABORATORY
043 - Clarke Co. | CLASSROOM/MULTI-PURPOSE
560 - Clifton Forge, City Of | CLASSROOM/OFFICE
570 - Colonial Heights, City Of | CLASSROOM/STUDIO
580 - Covington, City Of | CLEANING AND CAULKING
045 - Craig Co. | COMFORT STATION
047 - Culpeper Co. | COMMUNITY CULTURAL CENTER
049 - Cumberland Co. | CONSTRUCTION MANAGEMENT
590 - Danville, City Of | CONVOCATION CENTER
051 - Dickenson Co. | CORRECTIONAL
053 - Dinwiddie Co. | COURTHOUSE
595 - Emporia, City Of | DAM SAFETY
057 - Essex Co. | DATA/TELECOMMUNICATIONS
059 - Fairfax Co. | DEMOLITION
600 - Fairfax, City Of | DINING
610 - Falls Church, City Of | DOORS
061 - Fauquier Co. | DORMITORY
063 - Floyd Co. | DORMITORY/DINING
065 - Fluvanna Co. | ELECTRICAL
067 - Franklin Co. | ELEVATOR
620 - Franklin, City Of | EMERGENCY GENERATORS
069 - Frederick Co. | ENERGY MANAGEMENT SYSTEM
630 - Fredericksburg, City Of | ENVIRONMENTAL
640 - Galax, City Of | EQUIPMENT
071 - Giles Co. | EXCAVATION
073 - Gloucester Co. | EXTERIOR ELECTRICAL
075 - Goochland Co. | EXTERIOR MECHANICAL
077 - Grayson Co. | EXTERIOR WALL REPAIR
079 - Greene Co. | FENCE
081 - Greensville Co. | FIRE ALARM
083 - Halifax Co. | FIRE PROTECTION
650 - Hampton, City Of | FIRE STATION
085 - Hanover Co. | FISHING PIER
660 - Harrisonburg, City Of | FITNESS CENTER
087 - Henrico Co. | FLOORING
089 - Henry Co. | FOOD SERVICES
091 - Highland Co. | FOOT BRIDGE
670 - Hopewell, City Of | FOUNDATION
093 - Isle Of Wight Co. | FUEL FACILITY
095 - James City Co. | GREENHOUSE
097 - King And Queen Co. | GYM
099 - King George Co. | HATCHERY
101 - King William Co. | HOSPITAL
103 - Lancaster Co. | HOTEL
105 - Lee Co. | INFRASTRUCTURE
678 - Lexington, City Of | JUVENILE FACILITIES
107 - Loudoun Co. | LABORATORY
109 - Louisa Co. | LABORATORY/CLASSROOM
111 - Lunenburg Co. | LIBRARY
680 - Lynchburg, City Of | LIBRARY/STUDENT CENTER
113 - Madison Co. | LIFE SAFETY/FIRE SAFETY
685 - Manassas Park, City Of | LIGHTING
683 - Manassas, City Of | LIVESTOCK ARENA
690 - Martinsville, City Of | MAINTENANCE
115 - Mathews Co. | MAINTENANCE AREA
117 - Mecklenburg Co. | MAINTENANCE BUILDING
119 - Middlesex Co. | MAINTENANCE GARAGE
121 - Montgomery Co. | MAINTENANCE RESERVE
125 - Nelson Co. | MANUFACTURING
127 - New Kent Co. | MARINE CONSTRUCTION
700 - Newport News, City Of | MASONRY
710 - Norfolk, City Of | MECHANICAL
131 - Northampton Co. | MENTAL HEALTH FACILITY
133 - Northumberland Co. | MILLWORK
720 - Norton, City Of | MISCELLANEOUS
135 - Nottoway Co. | MISCELLANEOUS BUILDINGS
137 - Orange Co. | MISCELLANEOUS REPAIRS
139 - Page Co. | MONUMENT
141 - Patrick Co. | MULTI-PURPOSE
730 - Petersburg, City Of | MUSEUM
143 - Pittsylvania Co. | NURSING HOME
735 - Poquoson, City Of | OFFICE
740 - Portsmouth, City Of | OFFICE/CLASSROOM
145 - Powhatan Co. | OFFICE/INDUSTRIAL
147 - Prince Edward Co. | OFFICE/OTHER
149 - Prince George Co. | OFFICE/PARKING GARAGE
153 - Prince William Co. | OFFICE/RESIDENTIAL
155 - Pulaski Co. | OFFICE/WAREHOUSE
750 - Radford, City Of | OFFICE-BANK
157 - Rappahannock Co. | OFFICE-HIGH RISE
159 - Richmond Co. | OFFICE-MEDICAL
760 - Richmond, City Of | OFFICE-SHELL
161 - Roanoke Co. | OFFICE-TENANT UPFITS/BUILDOUTS
770 - Roanoke, City Of | OFFICE-UPFITS/BUILDOUTS
163 - Rockbridge Co. | OUTDOOR TRACK
165 - Rockingham Co. | PAINTING
167 - Russell Co. | PARKING GARAGE/DECK
775 - Salem, City Of | PARKING-SURFACE LOTS
169 - Scott Co. | PARKS
171 - Shenandoah Co. | PAVING
173 - Smyth Co. | PEDESTRIAN TRAIL
780 - South Boston, City Of | PERFORMING ARTS CENTER
175 - Southampton Co. | PHYSICAL EDUCATION
177 - Spotsylvania Co. | PICNIC SHELTERS
179 - Stafford Co. | PLANNING STUDY
790 - Staunton, City Of | PLUMBING
800 - Suffolk, City Of | PORTS
181 - Surry Co. | PRE-CONSTRUCTION
183 - Sussex Co. | RAILROAD TRACK
185 - Tazewell Co. | RECREATIONAL
810 - Virginia Beach, City Of | REGULATORY COMPLIANCE
187 - Warren Co. | REMEDIATION
191 - Washington Co. | RENOVATION-GENERAL
820 - Waynesboro, City Of | REPAIR SHOP
193 - Westmoreland Co. | RESEARCH FACILITY
830 - Williamsburg, City Of | RESIDENTIAL PROJECTS
840 - Winchester, City Of | RETAIL
195 - Wise Co. | ROADS
197 - Wythe Co. | ROOFING
199 - York Co. | SCULPTURE
999 - Unknown Or Multiple Locations | SECURITY ACCESS
SECURITY FENCE
SITE IMPROVEMENTS
SITEWORK
STADIUM
STAIRS
STEAM TUNNEL
STORAGE BUILDING
STRUCTURAL
STUDENT CENTER
SURVEY
SWIMMING POOL
TELECOMMUNICATIONS
TENNIS COURTS
TENT
THEATER
TRAINING FACILITIES
TREATMENT PLANTS
UST
UTILITIES
UTILITIES - ELECTRICAL
UTILITIES - HVAC
UTILITIES - MISC
UTILITIES - SEWER
UTILITIES - STEAM
UTILITIES - STEAM LINES
UTILITIES - STORMWATER
UTILITIES - TELECOMMUNICATIONS
UTILITIES - UST
UTILITIES - WATER
UTILITIES - WELLS & TANKS
UTILITIES - WWTP
VDOT - CHEMICAL BUILDING
VDOT - COMBO BUILDING
VDOT - FLAG POLES
VDOT - OFFICE/SHOP/STORAGE
VDOT - REPAIR SHOPS
VDOT - REST AREA CONCESSION
VDOT - SIGN CREW BLDG
VDOT - SPREADER RACK
VDOT - STORAGE BLDG
VDOT - TAILER
VDOT - TIMEKEEPER OFFICE
VDOT - TRAFFIC MANAGEMENT CTR
VDOT - VENDING SHELTER
VISITORS CENTER
WAREHOUSE
WAREHOUSE/OFFICE
WATERPROOFING
WINDOWS