ATTACHMENT “B”

Construction Manager at Risk

Preconstruction Scope of Services

The CM shall provide the following Basic Services and Additional Services (together the “Preconstruction Scope of Services”) for the Owner pursuant to all requirements of the Contract Documents:

Basic Services:

- Cost Study -   At each of the following phases of design, the CM shall prepare a detailed Cost Study, as described below, for the Project:

  - Schematic

  - Preliminary

  - Working Drawings

During the development of the Cost Study, the CM shall work closely with the A/E and the Owner to understand the various aspects of the design and components of the Project.

Each Cost Study shall include the following elements:

- A detailed cost estimate for all Work items and the methodology for establishing the value for each item.  All estimates shall be in an ASTM Uniformat II cost breakdown structure.

- Contingency shall be included in the detailed estimates in two categories: (1) Design Contingency; and (2) CM Contingency.  The value of the Design Contingency shall decrease at each design phase commensurate with the completeness of the Project documents. The CM Contingency shall be included in the detailed estimate at each design phase, including in the GMP at the working drawing stage, and shall be of sufficient value to cover those items identified to be paid from the CM Contingency as described in the CO-9CM(2) CM at Risk Contract.

- Pricing of alternate design options identified by the CM, the A/E or the Owner.

- Any clarifications and qualifications necessary to describe the specific assumptions made by the CM in the development of the estimate.

- Identification of all Project or other documents used in the development of the Cost Study or as the basis for any clarifications or qualifications.

- Value analysis or engineering options proposed by the CM, including the associated cost savings or added costs and any benefits/disadvantages related to each option.

- Identification of schedule requirements or demands requested by the Owner that increase total Project cost by more than 5 percent or any system or component by more than 10 percent.

- Comparison to previous Cost Studies by the CM (for preliminary or working drawings estimates) and the reason for any differences.

Prior to finalization of each Cost Study, the CM shall review the Cost Study with the A/E to confirm that the CM’s understanding of the Project and its components accurately represents the design intent of the A/E and that the costs and value analysis options in the Cost Study are appropriately representative of the A/E’s design intent.

- Constructability Review – The CM shall work with the Owner and the A/E to review the Project Plans, Drawings and Specifications to identify the feasibility and practicality of constructing the elements depicted therein relative to any Site constraints, required tolerances, Owner’s Total Construction Budget, cost of construction of each element, general availability of specified materials and equipment, and factors that may affect construction means and methods.

- Staging and Logistics Review – The CM shall work with the Owner and the A/E to establish the limits of construction, routes for deliveries, staging areas, parking areas for construction personnel, working hours, and any other items that affect the areas adjacent to the Project Site so as to limit the impact of construction activities to adjacent areas or operations while minimizing Project costs given the Site constraints.

- Cash Flow Forecasts – The CM shall provide, at the Owner’s request, forecasts of anticipated billings for the Project.  Such forecasts are for planning purposes only and shall not in any way dictate the actual billings or payments made during construction.

- Scheduling - Immediately following CM selection, the CM shall develop and submit a CPM schedule including both Part 1, Preconstruction, and Part 2, Construction Work.  The CM shall consult the A/E, Owner, governing entities, and other Project stakeholders to understand all Project activities, scheduling requirements and constraints, and projected timelines.  At a minimum, the CM shall thereafter update this CPM schedule monthly.  The CPM schedule and each update shall include, at a minimum, activities for: developing drawings and specifications for the various stages of design, the CM’s Cost Study activities, preliminary Project construction activities, permitting and other regulatory reviews, the value engineering and system analysis activities, key Owner and Project team decision dates, and Project milestones.

- System Analysis - The CM shall evaluate major systems and make pre-design recommendations to the Owner and A/E on which systems are most cost-effective.  The following systems shall be evaluated at a minimum:

  - Foundation and Structural Systems.

  - Building Envelope.

  - Vertical Transportation Systems

  - Plumbing Systems.

  - Mechanical Systems.

  - Electrical Systems.

  - Fire Protection Systems.

  - Building Automation/Mechanical Controls Systems.

  - Stormwater Management Systems.

- Progress Document Reviews – Throughout the entire design process, the CM shall make periodic reviews of the drawings and promptly advise the A/E and Owner on design decisions or elements that do not fit within the Owner’s Total Construction Budget or schedule.  These reviews should be performed as required by the Project demands but no less than monthly.

- Small Business Participation Plan – The CM shall, with the Owner, develop a plan for encouraging Small Business participation for the Project.

- Subcontractor Involvement and Prequalification - The CM shall solicit Subcontractor interest in the Project and prequalify interested and qualified trade contractors for the Part 2 Construction Work.  Pre-qualification criteria shall include experience, past performance, financial capability, technical capability, and quality capability.  If the Owner or A/E has an interest in including specific subcontractors, they shall be solicited and prequalified on the same basis as other subcontractors.  The CM shall procure the subcontracted work by publicly advertised, competitive sealed bidding to the maximum extent practicable.

- Subcontractor Bonding Policy

  - Insurance

The CM shall, with the Owner, establish an insurance policy concerning subcontractors.

Conventional subcontractor insurance provided in accord with the requirements of the CO-7CM is the default.  If Contractor Controlled Insurance Program (CCIP) is proposed by CM, the following is required within 30 days of the owner notifying the CM that the Schematic Design is complete:

    - Not-to-exceed fee for the CCIP stated as a percentage of the Cost of the Construction Work.

    - Details of and an itemized breakdown of the program for Owner review.  CM also agrees to permit Owner, or any consultants, engaged by Owner for purposes of reviewing the CCIP, to access and review the proposed CCIP. Any and all data requested by Owner or Owner’s consultant, on behalf of Owner, shall be provided by CM. Failure to provide any requested/required information will result in a rejection of the CCIP.

To fulfill the General Conditions of the Construction Contract Section 11, Contractors’ and Subcontractor’s Insurance certificate requirements, if CCIP is accepted by the Owner then the CM shall provide proof of the enrollment of all subcontractors in the CCIP concurrent with the submission of the CM’s proof of insurance to the Owner required at the time of construction award.

  - Bonding

The CM shall, with the Owner, establish a bonding policy concerning subcontractors. Failure to provide the requested/required information to the Owner may result in the rejection of any subcontractor bonding or Subcontractor Default Insurance (SDI) in favor of the CM’s Bond as required by the General Conditions.

Within 30 days of the Owner notifying the CM that the Schematic and Preliminary Design phases are complete, provide the following:

  - If conventional subcontractor bonding is proposed:

    - Proposed subcontractor bonding thresholds/requirements including the impacts, if any, on the CM’s bond.

    - Estimated cost for each trade to be bonded stated as a percentage of the Cost of the subcontract/trade package.

  - If SDI is proposed:

    - Maximum value of the coverage.

    - Details of and an itemized breakdown of the program for Owner review, including the impacts, if any, on the CM’s bond. CM also agrees to permit Owner or any consultants, engaged by Owner for purposes of reviewing the SDI, to access and review the proposed SDI. Any and all data requested by Owner or Owner’s consultant, on behalf of Owner, shall be provided by CM. Failure to provide any requested/required information will result in a rejection of the SDI.

    - Estimated cost of the insurance.

At the GMP the CM shall with the Owner, finalize the bonding policy concerning subcontractors, provide the following:

- If conventional subcontractor bonding is proposed:

- Final subcontractor bonding thresholds/requirements including the impacts, if any, on the CM’s bond.

- Cost for each trade to be bonded stated as a percentage of the Cost of the subcontract/trade package.

To fulfill the requirements of the subcontractor bonding policy, the CM shall provide proof that the appropriate subcontractor bonds have been obtained prior to application for the first progress payment.

- If Subcontractor Default Insurance is proposed:

- Maximum value of the coverage.

- Details of and an itemized breakdown of the program for Owner review, including the impacts, if any, on the CM’s bond. CM also agrees to permit Owner or any consultants, engaged by Owner for purposes of reviewing the SDI, to access and review the proposed SDI. Any and all data requested by Owner or Owner’s consultant, on behalf of Owner, shall be provided by CM. Failure to provide any requested/required information will result in a rejection of the SDI.

- Cost of the insurance.

To fulfill the requirements of the subcontractor bonding policy, the CM shall provide proof of the inclusion of the subcontractors in the SDI prior to application for payment.

Additional Services:

Agency to include any additional Pre-Construction services required of the CM.