ATTACHMENT “B”

Construction Manager at Risk

Preconstruction Scope of Services

The CM shall provide the following Basic Services and Additional Services (together the “Preconstruction Scope of Services”) for the Owner pursuant to all requirements of the Contract Documents:

Basic Services:

- Cost Study -   At each of the following phases of design,  the CM shall prepare a detailed  Cost Study, as described below, for the Project:

  - Schematic

  - Preliminary

  - Working Drawings

During the development of the Cost Study, the CM shall work closely with the A/E and the Owner to understand the various aspects of the design and components of the Project.

Each Cost Study shall include the following elements:

- A detailed cost estimate for all Work items and the methodology for establishing the value for each item.  All estimates shall be in an ASTM Uniformat II cost breakdown structure.

- Contingency shall be included in the detailed estimates in two categories:  (1) Design Contingency; and (2) CM Contingency.  The value of the Design Contingency shall decrease at each design phase commensurate with the completeness of the Project documents. The CM Contingency shall be included in the detailed estimate at each design phase, including in the GMP at the working drawing stage, and shall be of sufficient value to cover those items identified to be paid from the CM Contingency as described in the CO-9CM(2) CM at Risk Contract.

- Pricing of alternate design options identified by the CM, the A/E or the Owner.

- Any clarifications and qualifications necessary to describe the specific assumptions made by the CM in the development of the estimate

- Identification of all Project or other documents used in the development of the Cost Study or as the basis for any clarifications or qualifications.

- Value analysis or engineering options proposed by the CM, including the associated cost savings or added costs and any benefits/disadvantages related to each option.

- Identification of schedule requirements or demands requested by the Owner that increase total Project cost  by more than _5_ percent or any system or component by more than 10 percent

- Comparison to previous Cost Studies by the CM (for preliminary or working drawings estimates) and the reason for any differences.

Prior to finalization of each Cost Study, the CM shall review the Cost Study with the A/E to confirm that the CM’s understanding of the Project and its components accurately represents the design intent of the A/E and that the costs and value analysis options in the Cost Study are appropriately representative of the A/E’s design intent.

- Constructability Review – The CM shall work with the Owner and the A/E to review the Project Plans, Drawings and Specifications  to identify the feasibility and practicality of constructing the elements depicted therein relative to any Site constraints, required tolerances, Owner’s Total Construction Budget, cost of construction of each element, general availability of specified materials and equipment, and factors that may affect construction means and methods.

- Staging and Logistics Review – The CM shall work with the Owner and the A/E to establish the limits of construction, routes for deliveries, staging areas, parking areas for construction personnel, working hours, and any other items that affect the areas adjacent to the Project Site so as to limit the impact of construction activities to adjacent areas or operations while minimizing Project costs given the Site constraints.

- Cash Flow Forecasts – The CM shall provide, at the Owner’s request, forecasts of anticipated billings for the Project.  Such forecasts are for planning purposes only and shall not in any way dictate the actual billings or payments made during construction.

- Scheduling - Immediately following CM selection, the CM shall develop and submit a CPM schedule including both Part 1, Preconstruction, and Part 2, Construction Work.  The CM shall consult the A/E, Owner, governing entities, and other Project stakeholders to understand all Project activities, scheduling requirements and constraints,  and projected timelines.  At a minimum, the CM shall thereafter update this CPM schedule monthly.  The CPM schedule and each update shall include, at a minimum, activities for: developing drawings and specifications for the various stages of design, the CM’s Cost Study activities, preliminary Project construction activities, permitting and other regulatory reviews, the value engineering and system analysis activities, key Owner and Project team decision dates, and Project milestones.

- System Analysis - The CM shall evaluate major systems and make pre-design recommendations to the Owner and A/E on which systems are most cost-effective.  The following systems shall be evaluated at a minimum:

  - Foundation and Structural Systems.

  - Building Envelope.

  - Vertical Transportation Systems

  - Plumbing Systems.

  - Mechanical Systems.

  - Electrical Systems.

  - Fire Protection Systems.

  - Building Automation/Mechanical Controls Systems.

  - Stormwater Management Systems.

- Progress Document Reviews – Throughout  the entire design process, the CM shall make periodic reviews of the drawings and promptly advise the A/E and Owner on design decisions or elements that do not fit within the Owner’s Total Construction Budget or schedule.  These reviews should be performed as required by the Project demands but no less than monthly.

- Small Business Participation Plan – The CM shall, with the Owner, develop a plan for encouraging Small Business participation for the Project.

- Subcontractor Involvement and Prequalification - The CM shall solicit Subcontractor interest in the Project and prequalify interested and qualified trade contractors for the Part 2 Construction Work.  Pre-qualification criteria shall include experience, past performance, financial capability, technical capability, and quality capability.  If the Owner or A/E has an interest in including specific subcontractors, they shall be solicited and prequalified on the same basis as other subcontractors.  The CM shall procure the subcontracted work by publicly advertised, competitive sealed bidding to the maximum extent practicable.

- Subcontractor Bonding Policy - The CM shall, with the Owner, establish a bonding policy concerning subcontractors and other trade contractors.

Additional Services:

Agency to include any additional Pre-Construction services required of the CM.