## CM @ Risk
DGS-30-900
(Rev. 2/20)
Covered Institution Procurement Procedure Summary
for
Construction Management at Risk
COV = Code of Virginia
Criteria | Agency Procedure Item Number/Page Number
Construction Cost Considered (Relevant COV Sections: §2.2-4381.B.1, §2.2-4381.D.3)
Limited to Projects with Construction Cost in excess of $26,000,000 unless granted a written waiver (Relevant COV Sections: §2.2-4381.A)
Project Complexity Considered (Relevant COV Sections: §2.2-4381.B.1, §2.2-4381.D.4)
Building Use Considered (Relevant COV Sections: §2.2-4381.B.1, §2.2-4381.D.3)
Project Timeline Considered (Relevant COV Sections: §2.2-4381.B.1, §2.2-4381.D.3)
Value Eng. and/or Constructability Analysis Concurrent with Design Considered (Relevant COV Sections: §2.2-4381.D.5)
GMP Established at Working Drawings (Relevant COV Sections: §2.2-4381.A)
3-5 Offerors in Short List (Relevant COV Sections: §2.2-4381.A)
At least one DSBSD-Certified Small Business meeting minimum qualifications on Short List (Relevant COV Sections: §2.2-4381.A)
Interim GMP for Early Packages Permitted (Relevant COV Sections: §2.2-4381.D.5)
Need for Quality Control/Vendor Prequalification Considered (Relevant COV Sections: §2.2-4381.D.5)
Need for Cost/Design Contol Considered (Relevant COV Sections: §2.2-4381.D.5)
Need for Project Phasing Considered (Relevant COV Sections: §2.2-4381.D.5)
Written determination that Competitive Sealed Bidding is not Practicable or Advantageous (Relevant COV Sections: §2.2-4381.C.1)
Justification included in Request for Qualification (RFQ) (Relevant COV Sections: §2.2-4381.C.1)
Licensed Architect or Engineer employed or under contract to advise in use of CM@Risk (Relevant COV Sections: §2.2-4381.C.2)
30 Day RFQ Posting Time (Relevant COV Sections: §2.2-4381.C.3)
Include in RFQ and RFP if responses may be submitted electronically or via paper response (Relevant COV Sections: §2.2-4381.A)
Two Step Request for Qualifications/Request for Proposals (RFQ/RFP) Process (Relevant COV Sections: §2.2-4381.C.7)
Criteria for evaluation included in RFQ & RFP (Relevant COV Sections: §2.2-4381.C.1)
RFQ Evaluation shall include review of the Offeror's experience for 3 projects of similar program and size in the prior 10 years by any delivery method (Relevant COV Sections: §2.2-4381.A)
Contract Entered Into No Later than the Completion of Schematic Design Phase (Relevant COV Sections: §2.2-4381.C.4)
Prior CM@ Risk or BCOM (now DEB) Experience not a Prerequisite for award. (Relevant COV Sections: §2.2-4381.C.5)
90% of Construction Work Subcontracted Through Publicly Advertised Competitive Sealed Bidding to the Maximum Extent Practicable (Relevant COV Sections: §2.2-4381.C.6)